STATE WATER RESOURCES CONTROL BOARD

BOARD MEETING SESSION – CLEAN WATER PROGRAMS

SEPTEMBER 20, 2001

ITEM:  4

# SUBJECT

APPROVAL OF A STATE REVOLVE FUND (SRF) CAP INCREASE FROM $25 MILLION TO $50 MILLION FOR STATE FISCAL YEAR 2001/02; WASTEWATER EFFLUENT DISPOSAL/ GEYSERS RECHARGE PROJECT (PROJECT), CITY OF SANTA ROSA (CITY), SRF LOAN PROJECT NO. C-06-4062

# DISCUSSION

- On March 15, 2000, the State Water Resources Control Board (SWRCB) approved a preliminary loan commitment of $101 million for the construction of the Wastewater Effluent Disposal/Geysers Recharge Project.  This project constructs a 41-mile wastewater effluent disposal pipeline from the City to the Geysers geothermal area for steam field recharge.  Construction started in June 2000 and completion is projected for December 2002.  Because of significant litigation delays and increased construction costs, the project cost is now estimated at $131 million.

The projected $30 million construction cost increase is creating financial hardship for the City. The City will have to secure additional revenue bonds to finance the construction because of the SWRCB’s $25 million per year funding cap to individual agencies .  The City is requesting the SWRCB to increase the funding cap from $25 million to $50 million for State Fiscal Year 2001/02 for this energy producing facility.

# POLICY ISSUE

Should the SWRCB approve the request to increase the funding cap from $25 million to $50 million for State Fiscal Year 2001/02 for the City’s Wastewater Effluent Disposal/Geysers Recharge Project?

# FISCAL IMPACT

The SWRCB adopted Resolution No. 99-40 on May 20, 1999, which changed the method for deter-mining the amount of funding available for new SRF loans.  The adopted system is based on the availability of Federal Capitalization Grants, cash from SRF loan repayments and miscellaneous SRF investment earnings and takes into consideration actual and forecast cash disbursements for approved SRF loans.  The SWRCB adopted Resolution No. 2000-57 on July 20, 2000, which authorized the sale of up to $200,000,000 in revenue bonds if needed to maintain a positive cash flow in the SRF account.

A minimum cash balance of $25,000,000 will be maintained.  The SRF account balances, anticipated repayment amounts, and project approvals under consideration by the SWRCB in September 2001 are as follows:

|  | SFY | SFY | SFY | SFY | SFY |
| --- | --- | --- | --- | --- | --- |
|  | 2001-02 | 2002-03 | 2003-04 | 2004-05 | 2005-06 |
|  | ___________ | __________ | __________ | _________ | _________ |
| Beginning Balance: | $367,345,968 | $158,482,194 | $118,408,966 | $146,280,006 | $256,497,438 |
| Est. Repayments: | 102,501,878 | 119,669,710 | 152,769,359 | 163,658,307 | 172,999,687 |
| Revenue Bonds per Res. 2000-57 | 197,000,000 | -17,207,200 | -17,207,200 | -17,207,200 | -17,207,200 |
| Cap Grants: | 63,800,000 | 63,800,000 | 0 | 0 | 0 |
| Est. SMIF Interest: | 4,000,000 | 3,000,000 | 2,500,000 | 2,000,000 | 1,250,000 |
| Est. Disbursements: | -545,865,652 | -209,335,738 | -105,191,119 | -38,233.675 | -28,749,900 |
| Subtotal: | $188,782,194 | 118,408,966 | $151,280,006 | $256,497,438 | $384,790,025 |
| City of Santa Rosa (existing Commitment) | +25,000,000 | n/c | +1,000,000 |  |  |
| City of Santa Rosa C-06-4062 | -50,000,000 | n/c | -6,000,000 |  |  |
| Balance: | $158,482,194 | $118,408,966 | $146,280,006 | $256,497,438 | $384,790,025 |

# REGIONAL BOARD IMPACT

None

# STAFF RECOMMENDATION

The Division of Clean Water Programs recommends against waiving the Cap.

DRAFT  9/11/01

STATE WATER RESOURCES CONTROL BOARD

RESOLUTION NO. 2001-

INCREASE STATE REVOLVING FUND (SRF) CAP FROM $25 MILLION TO $50 MILLION FOR STATE FISCAL YEAR 2001/02; CITY OF SANTA ROSA (CITY); WASTEWATER EFFLUENT DISPOSAL/GEYSERS RECHARGE PROJECT (PROJECT); STATE REVOLVING FUND LOAN PROJECT NO. C-06-4062

WHEREAS:

- The State Water Resources Control Board (SWRCB) committed (per Resolution No. 2000-021) $101 million of SRF loan funds on March 15, 2000, for the City’s Project;

- The SRF funding cap for State Fiscal Year (SFY) 2001/02 was set at $25 million per agency according to Resolution No. 2001-075;

- The City is requesting the SWRCB to increase the SRF funding cap for the Project for SFY 2001/02 because of increased costs due to expansion of the energy producing capacity of the Project.  Specifically, the City is providing pipeline capacity for City of Healdsburg, Town of Windsor, and Sonoma County Water Agency to transport effluent to the Geysers for future power production.

THEREFORE BE IT RESOLVED THAT:

The State Water Resources Control Board approves a preliminary SRF loan commitment of $131 million for the construction of Wastewater Effluent Disposal/Geysers Recharge Project as follows:

State Fiscal Year 1999/2000	$25 million

State Fiscal Year 2000/2001	$25 million

State Fiscal Year 2001/2002	$50 million

State Fiscal Year 2002/2003	$25 million

State Fiscal Year 2003/2004	~$6 million

Repayment period of this loan shall be 20 years, and the first repayment shall be due one year after completion of construction for each contract.

CERTIFICATION

The undersigned, Clerk to the Board, does hereby certify that the foregoing is a full, true, and correct copy of a resolution duly and regularly adopted at a meeting of the State Water Resources Control Board held on September 20, 2001.

Maureen Marché

Clerk to the Board

# Footnotes

Est. repayments include repayments from existing loans and from loans forecast to be executed in the next few years for projects with existing commitments.

Resolution No. 2000-57 authorized the sale of $200,000,000 in revenue bonds.  It is estimated that the cost of issuing the bonds later this year will be $3,000,000 or 1 ½ percent.

EPA Capitalization Grants of $55,000,000 each for SFY’s 2001-02 and 2002-03 are forecast.  A 20% state match has been added and the 4% administrative allowance is deducted  from each of the forecast Cap grants.  Additional information regarding the FFY 2002 Cap. Grant may be available prior to the September board meeting.

Estimated disbursements include disbursements remaining on existing loans as well as disbursements anticipated on loans executed for projects with existing commitments (including FY 2000-01 commitments).  Each month the Division will revise the estimated disbursements total as cash draw forecasts are updated.