STATE WATER RESOURCES CONTROL BOARD

BOARD MEETING SESSION -- DIVISION OF CLEAN WATER PROGRAMS

NOVEMBER 16, 2000

# ITEM 9

# SUBJECT

APPROVAL OF A STATE REVOLVING FUND (SRF) LOAN FOR THE LAKE COUNTY SANITATION DISTRICT’S (DISTRICT) NORTHWEST REGIONAL WASTEWATER  TREATMENT PLANT IMPROVEMENTS, SRF LOAN PROJECT NO. C-06-4086-110

DISCUSSION

In accordance with the State Water Resources Control Board's (SWRCB) Policy for Implementing the State Revolving Fund for Construction of Wastewater Treatment Facilities (Policy), adopted on February 16, 1995, and last amended on June 18, 1998, projects on the adopted priority list need SWRCB approval to receive a SRF loan.  The SWRCB can issue a preliminary loan commitment after the Division of Clean Water Programs (Division) approves the Facilities Planning including the following: (1) the project report, (2) draft revenue program, (3) water conservation plan, and (4) environmental documents.  On August 30, 2000, the Division issued Facilities Plan Approval for the District’s Northwest Wastewater Treatment Plant Improvements. The District agreed in writing on October 3, 2000, with the Division’s approval.

The District is located in Lake County approximately120 miles northwest of Sacramento. The District’s wastewater treatment plant is located on the northwest corner of Clear Lake.  Wastewater flows to the Northwest Plant have recently exceeded treatment and disposal capabilities resulting in violation of regulatory waste discharge requirements and overflows of treated effluent to Clear Lake.  In February 1994, the Central Valley Regional Water Quality Control Board (CVRWQCB) issued a Cease and Desist Order mandating improvements to eliminate these violations by September 1, 2001.

The District has determined that improvements to collection, treatment, and disposal facilities are necessary to achieve compliance with CVRWQCB requirements. The proposed improvements to the collection system include replacement of pumps and pump station wet-wells and construction of approximately three miles of force main.  Improvements to the treatment plant will include a new septage receiving facility, grit chamber, modification to the headworks, conversion of existing oxidation ditches to fully mixed cells, addition of fully mixed lagoons, partially mixed cells, and a new sodium hypochlorite disinfection system.  Disposal system improvements will include construction of approximately 19 miles of effluent disposal pipeline from the Northwest plant to the Clear Oaks Wastewater Treatment Plant.  The District will receive Small Communities Grant funding for collection system improvements.

The District receives its water supply from both Clear Lake and ground water wells within the District’s limits.  The District has indicated that it has enough water resources available to serve the projected population.  In accordance with the Policy requirements for water conservation, the District has adopted a water conservation program consistent with local ordinances and authorities.

In accordance with the SRF Policy Section IX.(I), the District and the Division have agreed to establish a sunset date for initiating construction of May 1, 2001.  The Division may approve up to a 90-day time extension of this date for good cause.  The performance standards for this project, established upon approval of the Plans and Specifications, will be consistent with the District’s Waste Discharge Requirements as established under NPDES Permit No. CA0107433.

The District prepared a Draft Environmental Impact Report (EIR) for the proposed Wastewater Treatment and Disposal Facility Improvements Project that was distributed for public review and circulated through the State Clearinghouse (SCH #1997083008) from August 7, 1997, through September 22, 1997.  During the review period, comment letters were received from eleven agencies.  In addition, five individuals presented comments at a public hearing.  A wide variety of environmental issues were raised.

In October 1997, the District prepared a Final EIR that included comments, responses, and text revisions based on comments received.  The District adequately addressed the environmental issues raised during the review period.  The Lake County Planning Commission certified the Final EIR on October 23, 1997.  The District’s Board of Directors approved the project, certified the EIR, and adopted a Mitigation Monitoring and Operation Plan and a Statement of Overriding Considerations on November 4, 1997.  The District filed a Notice of Determination with the Lake County Clerk on November 13, 1997, and with the Governor's Office of Planning and Research on January 14, 1998.

Subsequent to approval of the Final EIR, the District expanded the project.  In conjunction with the Environmental Protection Agency, the District prepared an Environmental Assessment/ Finding of No Significant Impact (EA/FONSI) and Initial Study/Mitigated Negative Declaration (IS/MND) for the Clear Lake Basin 2000 – Phase II Project in October 1999.  The document was distributed to the public and circulated through the State Clearinghouse (SCH# 1999102005) from October 1, 1999, through October 29, 1999.  During the review period, the District received comment letters from two agencies, an Association, and four individuals.

The District prepared adequate responses to the comments.  On December 7, 1999, the District’s Board of Directors approved the project and adopted the MND and an Amended Mitigation Monitoring and Operation Plan.  The District filed a Notice of Determination with Lake County on December 29, 1999, and with the Governor’s Office of Planning and Research on January 10, 2000.

In May 2000, the Lake County Community Development Department (Department) prepared a Draft IS/MND for the Modification to Recycled Effluent Pipeline Alignment for the Clear Lake Basin 2000 Project.  The Draft IS/MND was distributed to the public and circulated through the State Clearinghouse (SCH# 2000062045) from June 12, 2000, through July 11, 2000.  No comments were received during the review period.  The District’s Board of Directors approved the proposed modifications and adopted the Mitigated Negative Declaration on August 24, 2000. The District filed a Notice of Determination with Lake County on August 24, 2000, and with the Governor’s Office of Planning and Research on August 28, 2000.

The estimated total project cost, including engineering and administration allowances, is $22.5 million.  Estimated SRF loan eligible costs for both treatment and disposal facilities are $15.9 million.  The District requests the SWRCB approve a loan of $15.9 million for this project with a 20-year repayment period.

POLICY ISSUE

Should the SWRCB conditionally approve an SRF loan for the proposed project, requiring construction initiation by May 1, 2001?

RWQCB IMPACT

The District lies within the CVRWQCB’s jurisdiction.  The proposed project will enable the District to comply with CVRWQCB requirements.

FISCAL IMPACT

The SWRCB adopted Resolution No. 99-40 on May 20, 1999, which changed the method for determining the amount of funding available for new SRF loans.  The adopted system is based on the availability of Federal Capitalization Grants, cash from SRF loan repayments and miscellaneous SRF investment earnings and takes into consideration actual and forecast cash disbursements for approved SRF loans.  The SWRCB adopted Resolution No. 2000-57 on July 20, 2000, which authorized the sale of up to $200,000,000 in revenue bonds if needed to maintain a positive cash flow in the SRF account.  A minimum cash balance of $25,000,000 will be maintained.  The SRF account balances, anticipated repayment amounts, and project approvals under consideration by the SWRCB in November 2000 are as follows:

|  | SFY | SFY | SFY | SFY | SFY |
| --- | --- | --- | --- | --- | --- |
|  | 2000-01 | 2001-02 | 2002-03 | 2003-04 | 2004-05 |
|  | ___________ | __________ | __________ | _________ | _________ |
| Beginning Balance: | $477,587,972 | $119,039,169 | $166,688,531 | $192,167,650 | $259,568,298 |
| Est. Repayments: | 89,140,059 | 105,524,802 | 125,965,442 | 149,792,604 | 151,798,892 |
| Revenue Bonds per Res. 2000-57 | 0 | 200,000,000 | -17,207,200 | -17,207,200 | -17,207,200 |
| Cap Grants: | 99,310,876 | 63,800,000 | 63,800,000 | 0 | 0 |
| Est. SMIF Interest: | 6,000,000 | 4,000,000 | 1,250,000 | 1,250,000 | 1,250,000 |
| Est. Disbursements: | -526,478,307 | -297,677,102 | -134,529,123 | -63,434,757 | -26,690,295 |
| Subtotal: | $145,539,169 | $194,688,531 | $205,967,650 | $262,568,298 | $368,719,695 |
| Lake Co. San. Dist. 4086-110 | -15,900,000 |  |  |  |  |
| City of Oceanside 4161-110 | -7,600,000 | -25,000,000 | 10,800,000 |  |  |
| City of Piedmont 4655-110 | -3,000,000 | -3,000,000 | -3,000,000 | -3,000,000 | -4,000,000 |
| Balance: | $119,039,169 | $166,688,531 | $192,167,650 | $259,568,298 | $364,719,695 |

### STAFF RECOMMENDATION

The SWRCB adopt a resolution approving a SRF loan of $15.9 million for the proposed project, with a repayment period of 20 years and the first repayment due one year after completion of construction.  In accordance with the Policy, the proposed resolution includes an expiration date for this preliminary loan commitment if the date of initiation of construction is not met.

STATE WATER RESOURCES CONTROL BOARD

RESOLUTION NO. 2000 - ___

APPROVAL OF A STATE REVOLVING FUND (SRF) LOAN FOR THE LAKE COUNTY SANITATION DISTRICT’S (DISTRICT) NORTHWEST REGIONAL WASTEWATER TREATEMENT PLANT IMPROVMENTS PROJECT

SRF PROJECT NO. C-06-4086-110

WHEREAS:

- The State Water Resources Control Board (SWRCB), on February 16, 1995, adopted the “Policy for Implementing the State Revolving Fund for Construction of Wastewater Treatment Facilities,” and most recently revised it on June 18, 1998;

- The SWRCB adopted the State Fiscal Year 1999 SRF Loan Program Priority List, on June 18, 1998, which included the District’s wastewater treatment plant improvements project in Priority Class C;

- The Division of Clean Water Programs has approved the facilities plan for the District’s project; and

4.	The Lake County Sanitation District has certified an Environmental Impact Report (State Clearinghouse No. 1997083008), and adopted two Mitigated Negative Declarations (SCH# 1999102005 and SCH# 2000062045) which have been reviewed and considered, and it has been determined that:

a)	The project could result in significant and unavoidable cumulative growth impacts to the area’s aesthetic, rural, and recreational quality;

b)	The project will result in the following benefits:

Eliminate unauthorized discharges of treated wastewater into Clear Lake that violate waste discharge requirements of regulatory agencies;

Remove the moratorium on new sewer connections and the associated Cease and Desist Order from the Central Valley Regional Water Quality Control Board;

Allow the District to come into regulatory compliance with waste discharge requirements;

Allow sewer connections to the system consistent with the planned growth projections identified in the County General Plan; and

Assist in implementation of the economic development and housing goals of the General Plan by providing infrastructure for homes, business, and industry.

c)  Changes or alterations have been required in, or incorporated into the proposed project, which avoid or reduce to less than significant levels the other potentially significant environmental effects identified in the EIR with respect to the following: (i) water quality impacts which will be mitigated by implementing erosion control, sediment/drainage controls, revegetation, spill protection, and road maintenance measures; (ii) threatened and endangered species which will be mitigated by ensuring that the project is implemented as presented in the July 1999 Biological Assessment Report prepared for the project, including all management and conservation measures; (iii) air quality impacts which will be mitigated by using best available technology and securing an Authority to Construct for the Lake County Air Quality Management District prior to commencing construction activities; and (iv) cultural resources impacts which will be mitigated by complying with the stipulations contained in the “Programmatic Agreement Among the U.S. EPA, the SWRCB, and the California State Historic Preservation Officer” developed for the proposed project;

d)  With respect to other potentially significant environmental impacts identified in the environmental document, appropriate changes or alterations are not within the responsibility and jurisdiction of the SWRCB.  Such other changes or alterations have been adopted or should be adopted by other agencies.

THEREFORE BE IT RESOLVED THAT:

The State Water Resources Control Board:

- Approves a SRF loan commitment of $15.9 million to the District for the improvement of the treatment and disposal facilities, with a repayment period of 20 years, and the first repayment due one year after completion of construction;

- Will withdraw this preliminary SRF loan commitment if the District does not initiate project construction by May 1, 2001.  The Division of Clean Water Programs may approve up to a 90 day extension for good cause;

- The performance standards for this project will be based on the District’s Waste Discharge Requirements; and

- Based on the above listed environmental benefits, adopts the following statement of overriding considerations to address the unmitigable significant cumulative impacts that may potentially occur from approval of the project:

Implementation of the proposed project would result in benefits to water quality, public health, and aquatic biota.  In balancing the project benefits against the potential significant cumulative impacts, the SWRCB finds that the public benefits of the project outweigh the unavoidable impacts and, therefore, determines that the impacts are acceptable.

CERTIFICATION

The undersigned, Administrative Assistant to the Board, does hereby certify that the foregoing is a full, true, and correct copy of a resolution duly and regularly adopted at a meeting of the State Water Resources Control Board held on November 16, 2000.

______________________________

Maureen Marché

Administrative Assistant to the Board

SFY 2000-01 revised beginning balance on 7-1-2000.

Est. repayments include repayments from existing loans and from loans forecast to be executed in the next few years for projects with existing commitments.

Resolution No. 2000-57 authorized sale of $200,000,000 revenue bonds if necessary.

An EPA Capitalization Grant for SFY 2000-01 is estimated to be $85,612,824 based on the version of the federal budget in the House Subcommittee bill.  Additional EPA Capitalization Grants of $55,000,000 each for SFY’s 2001-02 and 2002-03 are also forecast.  A 20 percent state match has been added and the 4 percent administrative allowance is deducted from each of the forecast Cap grants.

Estimated disbursements include disbursements remaining on existing loans as well as disbursements anticipated on loans executed for projects with existing commitments (including FY2000-01 commitments).  Each month the Division will revise the estimated disbursements total as cash draw forecasts are updated.