## Reissuance Schedule
San Francisco Bay Regional Water Quality Control Board
NPDES Wastewater Permit Issuance Schedule
Updated July 2018
[5 empty] | NPDES Permit Reissuance Schedule |  |  |  | U.S. EPA Contractor Support Schedule
| Order Number | Permit Number | Category | Permittee | Staff Assigned | Staff Review | Expiration Date | Target Adoption Date | U.S. EPA Support? | Support Level | Kick-Off | RPA & Limits | Draft Permit | Comments
19 | R2-2018-0003 | CA0038628 | MAJOR | CENTRAL MARIN SANITATION AGENCY |  |  | 2023-02-28 | Adopted 1/10/2018
25 | R2-2018-0004 | CA0037796 | MAJOR | PINOLE |  |  | 2023-03-31 | Adopted 2/14/2018
26 | R2-2018-0005 | CA0038369 | MAJOR | SILICON VALLEY CLEAN WATER |  |  | 2023-03-31 | Adopted 2/14/2018
23 | R2-2018-0010 | CA0037559 | minor | ORO LOMA AND CASTRO VALLEY, wet weather |  |  | 2023-12-31 | Adopted 3/14/2018
28 | R2-2018-0012 | CA0005240 | MAJOR | C&H SUGAR COMPANY |  |  | 2023-06-30 | Adopted 4/11/2018
29 | R2-2018-0016 | CA0037541 | MAJOR | SAN MATEO |  |  | 2023-06-30 | Adopted 5/9/2018
23 | R2-2018-0017 | CA0004880 | MAJOR | NRG, Pittsburg Power Plant |  |  | 2023-06-30 | Adopted 5/9/2018
31 | R2-2018-0024 | CA0038318 | MAJOR | BURLINGAME |  |  | 2023-07-31 | Adopted 6/13/2018
27 | R2-2018-0025 | CA0038067 | MAJOR | SAUSALITO-MARIN CITY SANITARY DISTRICT |  |  | 2023-07-31 | Adopted 6/13/2018
24 | R2-2018-0026 | CAG912004 | GENERAL | EXTRACTED GROUNDWATER General Permit |  |  | 2023-12-31 | Adopted 6/13/2018
32 | R2-2012-0094 | CA0037711 | MAJOR | SEWERAGE AGENCY OF SOUTHERN MARIN | Will Burrell |  | 2018-01-31 | 2018-08-08 | provided
30 | R2-2013-0027 | CA0037753 | minor | MARIN COUNTY SANITARY DISTRICT #5, Tiburon | James Parrish |  | 2018-09-30 | 2018-08-08 | no
| R2-2013-0012 | CA0029947 | minor | BROWNING-FERRIS INDUSTRIES Ox Mountain | John Madigan |  | 2018-06-30 | 2018-10-10 | provided |  |  |  |  | delayed
35 | R2-2013-0015 | CA0037788 | MAJOR | SAN FRANCISCO INTERNATIONAL AIRPORT | Patrick Karinja |  | 2018-06-30 | 2018-10-10 | provided
36 | R2-2013-0016 | CA0038539 | MAJOR | WEST COUNTY AGENCY | Vince Christian |  | 2018-06-30 | 2018-11-14 | provided
38 | R2-2013-0035 | CA0037885 | minor | CROCKETT COMMUNITY SERVICES DISTRICT, Port Costa | Will Burrell |  | 2018-11-30 | 2018-12-12 | provided
37 | R2-2013-0031 | CA0030058 | minor | BOTTLING GROUP | James Parrish |  | 2018-10-31 | 2019-01-09 | no
80 | R2-2009-0062 | CA0037681 | MAJOR | SAN FRANCISCO, Oceanside | Jessica Watkins |  | 2014-09-30 | 2019-02-13 | provided |  |  |  |  | Sent to EPA 4/2015
41 | R2-2013-0037 | CA0037532 | MAJOR | MILLBRAE | Patrick Karinja |  | 2019-01-31 | 2019-02-13 | no
40 | R2-2014-0010 | CA0030210 | MAJOR | LEHIGH PERMENENTE PLANT | John Madigan |  | 2019-04-30 | 2019-03-13 | no
45 | R2-2014-0024 | CA0037834 | MAJOR | PALO ALTO | Will Burrell |  | 2019-07-31 | 2019-04-10 | no
46 | R2-2014-0023 | CA0038091 | MAJOR | BENICIA | James Parrish |  | 2019-07-31 | 2019-05-08 | no
44 | R2-2014-0020 | CA0037800 | MAJOR | SONOMA VALLEY COUNTY SANITATION DISTRICT | TBD |  | 2019-06-30 | 2019-05-08 | yes | 1 | 2018-08-24 | 2018-09-07 | 2018-10-17
43 | R2-2014-0014 | CA0038873 | WATERSHED | SAN FRANCISCO BAY NUTRIENTS Watershed Permit | John Madigan |  | 2019-06-30 | 2019-05-08 | no
42 | R2-2014-0012 | CA0038130 | MAJOR | SOUTH SAN FRANCISCO-SAN BRUNO | Patrick Karinja |  | 2019-05-31 | 2019-06-12 | yes | 1 | 2018-11-23 | 2018-12-07 | 2019-01-16
34 | new | new | GENERAL | FIREWORKS General Permit | Marcos De La Cruz |  | new | SWRCB | no |  |  |  |  | R2 will draft permit for SWRCB consideration
39 | R2-2013-0029 | CA0037664 | MAJOR | SAN FRANCISCO, Southeast Plant | Jessica Watkins |  | 2018-09-30 | 2019-07-10 | no
47 | R2-2014-0030 | CA0038547 | MAJOR | DELTA DIABLO | TBD | 2018-09-30 | 2019-09-30 | 2019-10-10 | no
49 | R2-2014-0035 | CA0037621 | MAJOR | SUNNYVALE | Will Burrell | 2018-10-31 | 2019-10-31 | 2019-10-10 | no
48 | R2-2014-0034 | CA0037842 | MAJOR | SAN JOSE/SANTA CLARA | Will Burrell | 2018-10-31 | 2019-10-31 | 2019-10-10 | no
50 | R2-2014-0044 | CA0038440 | minor | EAST BAY MUNICIPAL UTILTIY DISTRICT, Wet Weather | Jessica Watkins |  | 2019-11-30 | 2020-01-15 | no
51 | R2-2014-0045 | CA0038792 | minor | EMERYVILLE, Sewage Collection System | Jessica Watkins |  | 2019-11-30 | 2020-01-15 | no
52 | R2-2014-0046 | CA0038474 | minor | ALAMEDA, Sewage Collection System | Jessica Watkins |  | 2019-11-30 | 2020-01-15 | no
53 | R2-2014-0047 | CA0038491 | minor | ALBANY, Sewage Collection System | Jessica Watkins |  | 2019-11-30 | 2020-01-15 | no
54 | R2-2014-0048 | CA0038466 | minor | BERKELEY, Sewage Collection System | Jessica Watkins |  | 2019-11-30 | 2020-01-15 | no
55 | R2-2014-0049 | CA0038512 | minor | OAKLAND, Sewage Collection System | Jessica Watkins |  | 2019-11-30 | 2020-01-15 | no
56 | R2-2014-0050 | CA0038504 | minor | PIEDMONT, Sewage Collection System | Jessica Watkins |  | 2019-11-30 | 2020-01-15 | no
57 | R2-2014-0051 | CA0038482 | minor | STEGE SANITARY DISTRICT, Sewage Collection System | Jessica Watkins |  | 2019-11-30 | 2020-01-15 | no
58 | R2-2015-0003 | CA0030180 | minor | CEDAR FAIR, Great America | John Madigan | 2019-03-01 | 2020-02-29 | 2020-02-12 | no
59 | R2-2015-0004 | CA0110116 | MAJOR | US NAVY, Treasure Island | TBD | 2019-04-01 | 2020-03-31 | 2020-03-11 | no
60 | R2-2015-0013 | CA0038024 | MAJOR | FAIRFIELD-SUISUN SEWER DISTRICT | Patrick Karinja | 2019-05-01 | 2020-04-30 | 2020-04-08 | no
61 | R2-2015-0018 | CA0037702 | MAJOR | EAST BAY MUNICIPAL UTILITY DISTRICT | Jessica Watkins | 2019-07-01 | 2020-06-30 | 2020-05-13 | no
62 | R2-2015-0021 | CA0037851 | MAJOR | LAS GALLINAS VALLEY SANITARY DISTRICT | Will Burrell | 2019-07-01 | 2020-06-30 | 2020-06-10 | no
63 | R2-2015-0029 | CA0038121 | minor | YOUNTVILLE |  |  | 2020-07-31
64 | R2-2015-0033 | CA0004961 | MAJOR | TESORO, Golden Eagle Refinery |  |  | 2020-08-30
65 | R2-2015-0034 | CA0037958 | MAJOR | NOVATO SANITARY DISTRICT |  |  | 2020-08-30
66 | R2-2015-0035 | CAG982001 | GENERAL | AGGREGATE MINING & SAND WASHING General Permit |  |  | 2020-08-30
67 | R2-2015-0037 | CA0005550 | MAJOR | VALERO, Benicia Refinery |  |  | 2020-09-30
68 | R2-2015-0041 | CA0038342 | minor | EAST BAY MUNICIPAL UTILITY DISTRICT, Orinda Potable Water |  |  | 2020-12-31
69 | R2-2015-0045 | CA0038733 | minor | UNION SANITARY DISTRICT, wet weather |  |  | 2020-12-31
70 | R2-2015-0052 | CA0006165 | MAJOR | ECOSERVICES (fomerly SOLVAY [formerly RHODIA]) |  |  | 2021-01-31
71 | R2-2016-0003 | CA0038016 | minor | ST HELENA |  |  | 2021-02-28
72 | R2-2016-0007 | CA0030198 | minor | EXPLORATORIUM |  |  | 2021-03-31
73 | R2-2016-0009 | CAG382001 | GENERAL | POTABLE WATER FILTER BACKWASH General Permit |  |  | 2021-03-31
74 | R2-2016-0018 | CA0037966 | minor | CALISTOGA |  |  | 2021-04-30
75 | R2-2016-0014 | CA0037810 | MAJOR | PETALUMA |  |  | 2021-05-31
76 | R2-2016-0015 | CA0038679 | minor | LIVERMORE-AMADOR VALLEY, Wet Weather |  |  | 2021-05-31
77 | R2-2016-0022 | CA0029904 | minor | CROCKETT COGENERATION |  |  | 2021-06-30
78 | R2-2016-0023 | CA0037770 | MAJOR | MT. VIEW SANITARY DISTRICT |  |  | 2021-06-30
1 | R2-2016-0035 | CA0037575 | MAJOR | NAPA SANITATION DISTRICT |  |  | 2021-08-31
2 | R2-2016-0042 | CA0037427 | minor | MARIN COUNTY SANITARY DISTRICT #5, Paradise Cove |  |  | 2021-11-30
3 | R2-2016-0043 | CA0005002 | MAJOR | USS-POSCO |  |  | 2021-12-31
4 | R2-2016-0044 | CA0005053 | MAJOR | PHILLIPS 66, San Francisco Refinery, Rodeo |  |  | 2021-12-31
5 | R2-2016-0045 | CA0030228 | minor | SCHNITZER |  |  | 2021-12-31
6 | R2-2016-0047 | CA0005134 | MAJOR | CHEVRON, Richmond Refinery |  |  | 2022-01-31
7 | R2-2017-0007 | CA0030201 | minor | NAPA SALT POND RESTORATION |  |  | 2022-05-31
8 | R2-2017-0008 | CA0038768 | MAJOR | AMERCIAN CANYON |  |  | 2022-05-31
9 | R2-2017-0009 | CA0037648 | MAJOR | CENTRAL CONTRA COSTA SANITARY DISTRICT |  |  | 2022-05-31
10 | R2-2017-0013 | CA0038776 | MAJOR | PACIFICA |  |  | 2022-05-31
11 | R2-2017-0016 | CA0037869 | MAJOR | EAST BAY DISCHARGERS AUTHORITY, Joint Outfall |  |  | 2022-06-30
12 | R2-2017-0017 | CA0037613 | MAJOR | DUBLIN SAN RAMON & LIVERMORE-AMADOR VALLEY |  |  | 2022-06-30
13 | R2-2017-0018 | CA0038008 | MAJOR | LIVERMORE |  |  | 2022-06-30
14 | R2-2017-0026 | CA0037737 | MAJOR | NORTH SAN MATEO COUNTY SANITATION DISTRICT |  |  | 2022-08-31
15 | R2-2017-0027 | CAG032012 | GENERAL | DRY DOCK General Permit |  |  | 2022-08-31
18 | R2-2017-0034 | CA0037826 | MAJOR | RODEO SANITARY DISTRICT |  |  | 2022-10-31
17 | R2-2017-0035 | CA0037699 | MAJOR | VALLEJO FLOOD & WASTEWATER DISTRICT |  |  | 2022-10-31
20 | R2-2017-0039 | CA0005789 | MAJOR | SHELL OIL, Martinez Refinery |  |  | 2022-11-30
21 | R2-2017-0040 | CA0038598 | MAJOR | SEWER AUTHORITY MID-COASTSIDE |  |  | 2022-12-31
22 | R2-2017-0041 | CA0038849 | WATERSHED | SAN FRANCISCO BAY MERCURY & PCBs Watershed Permit |  |  | 2022-12-31
16 | R2-2017-0048 | CAG912002 | GENERAL | GROUNDWATER FUELS & VOCs General Permit |  |  | 2023-06-30
79 |  |  |  | Unscheduled permits:
81 | R2-2011-0058 | CA0038636 | MAJOR | EAST BAY REGIONAL PARK DISTRICT, Hayward Marsh |  |  | 2016-10-31 | [6 empty] | Discharger likely to cease discharge
Formulas:
Staff Review = [Expiration Date]-365

## Percent Up-to-Date
Board Meeting | 2018-07-31 | 2018-08-30 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01
Total Number of Permits | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
Number of Expired Permits | 6 | 5 | 5 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Permits Reissued |  | 2 | 0 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 0 | 0 | 3 | 0 | 0 | 8 | 1 | 1 | 1 | 1 | 1 | 0
New Permits Adopted |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permits Rescinded |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permits to Expire |  | 0 | 0 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 1 | 2 | 8 | 0 | 0 | 1 | 1 | 1 | 0 | 2
Permits Processed Early |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Expiration Averted |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 2
Percent Up-to-Date | 92.5 | 93.75 | 93.75 | 95 | 95 | 95 | 96.25 | 97.5 | 97.5 | 97.5 | 97.5 | 97.5 | 98.75 | 98.75 | 98.75 | 98.75 | 98.75 | 88.75 | 98.75 | 98.75 | 98.75 | 98.75 | 98.75 | 98.75 | 98.75