## Sheet1
Feb 23 2006 version of mercury BMP table for MRP
Description of Action and Objectives | Category | Steps1 | Reporting Requirements and Desired Outcome1 | Comments/References | First Permit Term
1. Pollution Prevention/Source Control/Erosion Control
1.1 Collection and Recycling of Mercury containing materials (thermostats/switches/bulbs) | 1 (already happening throughout region due to Universal Waste Rule) | 1. Evaluate implementation challenges and lessons learned regarding collection and recycling mandated through UWR by surveying affected businesses and buildings. Develop recommendations for ways in which program can facilitate proper collection and disposal conducted through such efforts. | Report on step 1 results | · Based on estimated mass, the priority medium and large businesses and municipal facilities. Lowest priority is residential component. | Joint Program
| 1 | 2. Implement recommendations developed through step 1 report.
1.2.1 Evaluate managing Hg-containing materials and wastes during construction, including building demolition and improvement (e.g., light bulbs, switches, etc.) activities. The goal is to determine whether municipalities should implement this type of program. | 4 | 1. Evaluate potential presence of POCs (including Hg and PCBs) at construction sites, current material handling and disposal regulations/programs (e.g., municipal ordinances, RCRA, TSCA) and current level of implementation. | Report that evaluates current regulations and level of implementation and identifies shortfalls (complete by end of Year 1). | Include other POCs in this program. Include researching lessons learned from asbestos abatement programs and possible future tie-in. | Joint Program
|  | 2. Develop sampling and analysis plan (includes research on when, where and which construction materials potentially contained PCBs). | Prepare sampling and analysis plan (complete by end of Year 2). |  | Joint Program
|  | 3. Implement sampling and analysis program. | Prepare report with results and recommendations for next steps (complete by end of Year 3 or 4). | Decision Point: do the results of the sampling and analysis indicate the need to develop a pilot program to manage Hg-containing material and wastes during building demolition and improvement? | One Case Study per Program
1.2.2 Construction site erosion control. The goal is to ensure that current construction site stormwater pollution programs minimize or prevent discharges of sediment and potentially associated particle-bound POCs. | 1 | 1. Confirm that existing construction site erosion control programs are fully implemented. | Report evaluating program effectiveness and recommending improvements, if needed (complete by end of Year 1). | Decision Point: based on the level of success of program, maintain at current level, expand, scale back or discontinue. | Full Implementation
2. Drainage-focused investigation and abatement
2.1 Investigate and abate on-land drainages with elevated Hg concentrations | 3 (but with multiple locations probably) | 1. Conduct desktop/GIS study in which the data layers are: geologic formations and known mercury mines, potential air sources, past and current landuse, measured concentrations, location of metal cleaners and small recyclers. Suggested concentration screen is 2 ppm (normalized to % fines). | Report detailing selection of small number of pilot study areas based on desktop analysis. Report should also identify sampling sites within the case study regions (complete by end of Year 1). |  | Each Program does this step. Perform investigation on 5 pilot sites per program
|  | 2. For selected pilots locations, groundtruth the results from step 1 by conducting an Ettie-like recon in the drainage. Look in storm drains and conveyances. Test sediments in storm drains and conveyances to characterize the extent and magnitude of concentrations. | A report on the spatial extent, concentrations, storm drain characteristics for the pilot sites. This report can also start to sketch out recommendations for which sites require further characterization work or abatement | Decision: do results of the sampling and analysis indicate that an abatement program is needed? | Each Program does this step
|  | 3. Identify funding and responsible parties (same as PCBs) | Report on proposed remedial activities, funding, and agency oversight | See CEP project 4.28 possibly | Each Program does
|  | 4. Conduct Abatement program | Report results of pilot program effectiveness and lessons learned by end of Year 4 | Decision: based on level of success of the case studies, maintain, expand, or scale back the number of studies or discontinue | 3 case studies per program
3. Soil/Sediment Control (need to fill in soon)
3.1 Increased routine sediment management practices
· Stormwater inlet cleaning |  | Expand existing programs | · Evaluate benefits to increase, retrofit, or optimize current practices |  | Joint Program
· Catch basin/pump station cleaning |  | · Enhance degree to which these practices are targeted to areas of high concentrations | · Report effectiveness of current management practices to reduce loads |  | Joint Program
· Street sweeping
4. Stormwater Treatment
4.1 Stormwater runoff treatment retrofits for fine sediment control | 4 | 1. Identify locations that present opportunities to install treatment systems (i.e. detention basins, sand filters, infiltration basins, wetlands) along with an assessment of the best option for those locations. This assessment should identify potential sites draining a variety of landuse types throughout all program areas and discuss feasibility/economonic issues. | Report on candidate sites and proposed treatment type for those sites. Report should include assessment of at least 15 sites spanning program areas. | This should be a year 1 task shared by all programs. | Joint Program
| 3 | 2.Based on first stage report, select sites to perform pilot studies. Pilots should be conducted such that they span treatment types and drainage characteristics. | Report status/results/lessons learned at end of permit term. | want commitment to a long term implemntation and data collection to make sure we get a robust data set for analyssis of this technique. | One pilot per program area
4.2 Stormwater treatment by POTWs | 4 | 1. Prepare list of existing pump stations in the region and evaluate what they drain and the feasibility of routing to POTWs. The purpose is to identify candidate opportunities. Also work with BACWA to work out program structure, including cost sharing agreements. | Submit report on the list of pump stations, their drainages and feasibility considerations with routing to POTW for each pump station. | Need to work cooperatively with BACWA and share workload among programs. Evaluate drainage areas, flow volume, contaminant benefit, and timing. | Joint program
| 3 | 2. Implement pilot studies in locations to represent a range of conditions and landuses. | Submit report on the implementation status and monitoring results within 5 years. | Need to establish manner of measuring benefit (probably straightforward) as well as how to distribute this benefit to WW and UR partners. The Water Board would like to see a commitment to long-term monitoring of the pilot locations. | One pilot per program area
6.Other Activities
6.1 Development of a risk reduction program |  | · Develop and implement a risk reduction strategy to mitigate |  |  | Joint program
|  | · Participate in regional risk reduction program | Reporting?
6.2 Fate and Transport Studies |  | · Identify particular information needs consistent with this BP obligation | Reporting? |  | joint program
Conduct or cause to be conducted studies aimed at better understanding mercury fate, transport, and biological uptake in San Francisco Bay and tidal areas |  | · Identify studies ongoing that are accomplishing a portion of this
We need to understand the fate and transport and effects of mercury discharged in urban runoff and have a way to compare these features to mercury entering the Bay from other source categories |  | · Plan for filling data gaps
6.3 Consult with Caltrans regarding Caltrans portion of allocation |  | · Develop an equitable allocation-sharing scheme in consultation with Caltrans (see BPA and Staff Report for explanation) to address Caltrans roadway and non-roadway facilities in the program area, and report the details to the Water Board; | · self-explanatory |  | joint program
6.4 Attempt to secure bond funding for system improvements | 4 | Investigate SOCAL experience in securing bond funding for system retrofits and improvements. Pursue such funding with Water Board support as appropriate. |  |  | joint program
7. Monitoring Activities
7.1 Stormwater Loads or Loads avoided |  | Develop and implement long-term monitoring plan | · While developing program to accomplish above measures, submit proposal to water board regarding credit to be given and rationale
· Develop and implement a monitoring system to quantify either mercury loads or loads reduced through treatment, source control, and other management efforts; |  | If measuring loads avoided: | Report on loading study/loads avoided results |  | joint program
· Demonstrate progress toward (a) the interim loading milestone, or (b) attainment of the program area allocations, by using one of the following methods: |  | Establish criteria for credit to be given for certain types of actions |  |  | each program responsible
Quantify loads avoided through program activities
1) Quantify the annual average mercury load reduced by implementing (a) pollution prevention activities, and (b) source and treatment controls. The benefit of efforts to reduce mercury-related risk to wildlife and humans should also be quantified.
2) Quantify the mercury load as a rolling five-year annual average using data on flow and water column mercury concentrations. |  | Conduct baseline loading measurements or quantify loads avoided
3) Quantitatively demonstrate that the mercury concentration of suspended sediment that best represents sediment discharged with urban runoff is below the suspended sediment target. |  | During first permit term, the programs should be able to demonstrate achievement of a load avoided goal totaling 20 kg/year (this is 25% of the load avoided necessary to reach the load allocation).
7.2 Methyl Mercury Monitoring | 3 | Conduct monthly methylmercury monitoring at 5 lower watershed sites in several (5) drainages for methylmercury for 1 year. The objective of the monitoring is to investigate a representative set of drainages and obtain seasonal information. | Report on site selection rationale and monitoring results | need to get a handle on the magnitude and spatial/temporal patterns of methylmercury. Need to do mercury at the same time as well. Do not need loading study but just information at this point. | joint program