## Table 2
Minimum Control Measure | BMP # | Activity/Best Management Practices | [5 empty] | Implementation Plan | Measurable Goal | Message(s)/Pollutants Addressed | Target Audience(s) | Implementer(s)
|  |  | FY 05/06 | FY 06/07 | FY 07/08 | FY 08/09 | FY 09/10
Public Education and Outreach | 1a. | North Coast Storm Water Coalition | X |  |  |  |  | Finalize six posters educating public on storm water impacts of pet wastes, leaking oil, hazardous waste disposal, car washing, cigarette butts, and fertilizers and pesticides | Existing storm water pollution prevention workplans identified / developed | Pet Waste, hydrocarbons, hazardous materials, sediment, cigarette butts, fertilizers & pesticides | Pet owners, home owners, general public | City Public Works Director, North Coast Storm Water Coalition
| 1b. |  |  | X | X | X | X | Distribute posters to school, city agencies, and general public | 100 % of school and government participation tracked | Pet Waste, hydrocarbons, hazardous materials, sediment, cigarette butts, fertilizers & pesticides | Pet owners, home owners, general public | City Public Works Director, North Coast Storm Water Coalition
| 1c. |  | X | X | X | X | X | Develop storm water web site | Increase content on web site by a minimum of 10 % each year | Storm water awareness | general public, contractors, home owners, school children | City Public Works Director, North Coast Storm Water Coalition
| 1d. |  |  | X |  |  |  | Identify additional public education and outreach task to benefit all members of Coalition | Identification of next public education and outreach project with established action plan and implementation schedule | Storm water awareness | unknown at this time | City Public Works Director, North Coast Storm Water Coalition
| 2a. | Reaches To Beaches | X |  |  |  |  | Survey all schools in City for interest in participation in program | 100 % of schools contacted and response on interest obtained | Storm water awareness | High School students | City Public Works Director
| 2b. |  |  | X |  |  |  | Coordinate with RCAA on identifying staff to implement program | Training staff and schools identified for program participation | Storm water awareness | High School students | City Public Works Director, RCAA
| 2c. |  |  | X | X | X | X | Implement Program at local schools | Program implemented in at least one school per year, with goal of providing program to each interested school within five years | Storm water awareness | High School students | City Public Works Director, RCAA
| 3a. | Educational Component of Existing Commercial and Industrial Inspections | X | X | X | X | X | Coordinate with the City's Pre-Treatment Coordinator, County CUPA Program, and County Used Oil Program Coordinator to ensure that all industrial and applicable commercial businesses within the City receive storm water educational materials at least once during the permit term. | 100 % of inspected businesses receive storm water educational materials by the end of the permit term | Hydrocarbons, Illicit discharges | Industrial and Commercial Businesses | City Public Works Director, City Pre-Treatment Coordinator, County Used Oil Program Coordinator, CUPA Staff
| 4 | Pet Waste Signs | X | X | X | X | X | Identify appropriate locations and install pet waste kiosks with signage and bag dispenser at appropriate parks and other public recreational areas within the City encouraging the public to pick up after their pet. | Install at least 5 new kiosks by the end of the permit term. | Nutrients | Pet Owners | City Public Works Director
| 5a. | Storm Drain Marking | X | X | X | X | X | Coordinate with County Used Oil Program, Reaches to Beaches students, and City Pre-Treatment Coordinator on storm drain stenciling opportunities | 100 % of storm drains stenciled by end of permit term | Storm Water Pollution Prevention | General Public, school children | City Public Works Director
| 5b. |  |  | X | X | X | X | Amend storm drain design standards to require developers to install cast iron embossed covers with a no dumping message on all new storm drains | 100 % compliance | Storm Water Pollution Prevention Message | Developers | City Engineer
Public Education and Outreach | 6a. | Storm Water Hotline | X |  |  |  |  | Establish Storm Water Hotline | Dedicated phone number established for use as storm water hotline | Sediment, hydrocarbons and other hazardous materials | General Public | City Public Works Director
| 6b. |  | X |  |  |  |  | Establish Tracking Sheet for use by Hotline Operator to track complaint and action taken | Tracking sheet | Sediment, hydrocarbons and other hazardous materials | General Public | City Public Works Director
| 6c. |  |  | X | X | X | X | Advertise the Storm Water Hotline number on all educational pamphlets, posters, and storm water web site developed with the North Coast Storm Water Coalition | 25 % Compliance each fiscal year for 100 % compliance by end of permit term | Sediment, hydrocarbons and other hazardous materials | General Public | City Public Works Director
| 7a. | Educational Outreach to Public | X | X | X | X | X | Distribute storm water educational materials at appropriate activities held at the Adorni Center | Educational materials handed out at a minimum of one event per year over the permit term | Priority pollutants, storm water awareness | Public | City Public Works Director
| 7b. |  |  | X | X | X | X | Provide free educational materials at City Hall | Storm water educational materials available at City Hall 100 % of the time. | Priority pollutants, storm water awareness | Public | City Public Works Director
| 7c. |  | X | X | X | X | X | Develop and submit storm water program related public service announcements to local radio station or newspaper. | At least 1 public service announcement submitted per year | Storm water awareness | Public | City Public Works Director
| 7d. | Community Spring Cleanup Day | X | X | X | X | X | Advertise the Community Spring Cleanup Day and hold event to clean up City Parks, neighborhoods, waterfront and streams | Cleanup Day held each year and advertised in at least three local media outlets annually | Public Involvement and education | Public | City Public Works Director
| 7e. | Construction Pamphlets |  | X |  |  |  | Develop a series of pamphlets describing City's new Storm Water Ordinance and BMP Manual and permitting requirements | Pamphlets developed. | Sediment, Storm water pollution prevention | Construction Contractors & Developers | City Public Works Director
| 7f. |  |  |  | X | X | X | Distribute pamphlets during pre-construction meetings and construction site inspections | Pamphlets handed out to 100 % of contractors at pre-development meetings and 100 % of construction site inspections. | Sediment, Storm water pollution prevention | Construction Contractors | City Plan Checkers and Construction Inspectors
Public Involvement/ Participation | 1a. | Humboldt Bay First Flush Study | X | X | X | X | X | Coordinate with City of Arcata, Humboldt County, and RCAA to advertise First Flush Study and seek volunteers | Run at least five advertisements in local media each summer seeking volunteers | Sediment and priority pollutants | General Public | City Public Works Director, City of Arcata Environmental Planning, County Division of Environmental Health, RCAA
| 1b. |  | X | X | X | X | X | Identify and train at least 20 volunteers to perform first flush sampling | Train at least 20 volunteers to perform First Flush sampling | Sediment and priority pollutants | General Public | City Public Works Director, City of Arcata Environmental Planning, County Division of Environmental Health, RCAA
| 1c. |  | X | X | X | X | X | Perform First Flush Sampling Annually | Perform First Flush sampling each year at a minimum of 8 sampling locations within the City | Sediment and priority pollutants | General Public | City Public Works Director, City of Arcata Environmental Planning, County Division of Environmental Health, RCAA
| 1d. |  |  | X | X | X | X | Evaluate the first flush sampling results to develop future SWMP policy, including outreach BMPs as appropriate. | As needed, educational outreach BMPs developed to specifically address pollutants identified in the first flush sampling | Sediment and Priority pollutants | City Public Works Director | City Public Works Director
Public Involvement/ Participation | 2a. | Reaches To Beaches | X |  |  |  |  | Survey all schools in City for interest in participation in program | 100 % of schools contacted and response on interest obtained | Storm water awareness | High School students | City Public Works Director
| 2b. |  |  | X |  |  |  | Coordinate with RCAA on identifying staff to implement program | Training staff and schools identified for program participation | Storm water awareness | High School students | City Public Works Director, RCAA
| 2c. |  |  | X | X | X | X | Implement Program at local schools | Program implemented in at least one school per year, with goal of providing program to each interested school within five years | Storm water awareness | High School students | City Public Works Director, RCAA
| 3 | Community Spring Cleanup Day | X | X | X | X | X | Hold the Community Spring Cleanup Day to get public involved in cleaning up City Parks, neighborhoods, waterfront and streams | Cleanup Day held each year | Public Involvement and education | Public | City Public Works Director
| 4a. | Storm Drain Stenciling | X | X | X | X | X | Coordinate with County Used Oil Program, Reaches to Beaches students, and City Pre-Treatment Coordinator on storm drain stenciling opportunities | 100 % of storm drains stenciled by end of permit term | Storm Water Pollution Prevention | General Public, school children | City Public Works Director
| 4b. |  |  | X | X | X | X | Hold at least one storm drain marking event with the public each year | 100 % compliance | Storm Water Pollution Prevention Message | General Public | City Engineer
Illicit Discharge Detection and Elimination | 1a. | Identifying Illicit Discharges |  | X | X | X | X | Coordinate with City's Pre-Treatment Coordinator on inspections of permitted industrial dischargers and complaint response | Determine areas of concern to be targeted for outreach and maintenance. | Illicit Discharges | Permitted Industrial dischargers | City Public Works Director and Pre-Treatment Coordinator
| 1b. |  |  | X | X | X | X | Track complaints received through Public Works Department. Maintain records of follow-up activities to show that discharges are adequately addressed. | 100 % corrective action | Illicit Discharges | Permitted Industrial dischargers | City Public Works Director and Pre-Treatment Coordinator
| 1c. |  | X | X | X | X | X | Enforce water waste prohibition. | 100 % corrective action | Priority Pollutants | Permitted Industrial dischargers | City Public Works Director and Pre-Treatment Coordinator
| 2a. | Storm Water Hotline | X |  |  |  |  | Establish Storm Water Hotline | Dedicated phone number established for use as storm water hotline | Sediment, hydrocarbons and other hazardous materials | General Public | City Public Works Director
| 2b. |  | X |  |  |  |  | Establish Tracking Sheet for use by Hotline Operator to track complaint and action taken | Tracking sheet | Sediment, hydrocarbons and other hazardous materials | General Public | City Public Works Director
| 2c. |  |  | X | X | X | X | Forward complaints of illicit discharges to City Pre-Treatment Coordinator, County Environmental Health or other appropriate personnel | 100 % follow-up on all illicit discharge complaints | Sediment, hydrocarbons and other hazardous materials | General Public | City Public Works Director
| 2d. |  |  | X | X | X | X | Review complaint logs to identify areas or target audience where additional inspections or education is required | 100 % review of complaint logs | Sediment, hydrocarbons and other hazardous materials | City Public Works Director | City Public Works Director
Illicit Discharge Detection and Elimination | 3a. | Storm Water GIS | X |  |  |  |  | Complete the City's Storm Water GIS web site | Document and enforce 100 % of illicit connections identified | Storm water awareness | General Public | City Public Works Director
| 3b. |  |  | X |  |  |  | Advertise the existence of the GIS web site to the public and other agencies through GIS user's group meetings and providing link on Storm Water web site. | Monitor hits and comments on the web site. Use hit rate to determine if additional advertising is required | Storm water awareness | General Public | City Public Works Director
| 4a. | Storm Water Ordinance | X |  |  |  |  | Complete Draft Storm Water Quality Management and Discharge Control ordinance | Draft Ordinance finalized | Illicit Discharges | Public | City Public Works Director
| 4b. |  | X |  |  |  |  | City Attorney and City Engineer to review storm water ordinance | Storm water ordinance reviewed and revised | Illicit Discharges | City Attorney, Public Works Director, City Engineer | City Attorney, Public Works Director, City Engineer
| 4c. |  |  | X |  |  |  | Present ordinance to City Council | Storm water ordinance adopted | Illicit Discharges | City Council | City Public Works Director
| 4d |  |  | X |  |  |  | Public Works to conduct in-house training related to ordinance enforcement | 100 % of applicable Public Works staff receive training | Priority Pollutants, Illicit Discharges | Public Works staff | City Public Works Director
| 4e |  |  | X | X |  |  | Include information on the storm water ordinance in public service announcements | Information on the storm water ordinance included in at least 1 public service announcement | Illicit discharges | Public | City Public Works Director
| 4f |  |  | X | X | X | X | Oversee implementation and enforcement of ordinance | Enforce 100 % of observed illicit discharges | Priority Pollutants, Illicit Discharges | Public | City Public Works Director
| 5a. | Commercial & Industrial Inspections |  | X |  |  |  | Coordinate with City Pre-Treatment Coordinator, County Division of Environmental Health, and County CUPA to develop form to track illicit connections, spills, and discharges | Form developed and used to track 100 % of illicit connection, spills, and discharges | Illicit Discharges | City Public Works, Pre-Treatment Coordinator, County DEH, & County CUPA employees | Public Works Director, County CUPA & DEH staff
| 5b. |  |  | X | X | X | X | Track the locations of illicit discharges to determine areas of concern to be targeted for outreach and additional monitoring / maintenance | Areas of concern identified and additional outreach, monitoring and maintenance conducted | Illicit Discharges | Areas of concern to be identified | City Public Works Director
| 5c. |  |  | X | X | X | X | Obtain and evaluate results of commercial / industrial inspections performed by the Cit Pre-Treatment Coordinator, County DEH, and County CUPA | Evaluate inspection results to determine areas of concern to be targeted for outreach and additional monitoring / maintenance | Illicit Discharges | City Public Works, Pre-Treatment Coordinator, County DEH, & County CUPA employees | City Public Works Director
| 5d. |  |  |  | X | X | X | Perform additional outreach, monitoring, and maintenance as necessary | Additional outreach, monitoring, and maintenance performed to 100 % of identified areas of concern | Illicit Discharges | Areas of concern to be identified | City Public Works Director
| 6a. | Smoke Testing & Illicit Connection Detection & Elimination |  | X |  |  |  | Develop operations plan with schedule and tracking system for performing smoke testing of the storm drain system | Operations Plan, Schedule & Tracking Systems developed | Illicit Connections, groundwater infiltration | Property Owners, City Public Works Director | City Public Works Director
| 6b. |  |  | X | X | X | X | Perform Smoke Testing of the System | A minimum of 10% of the system smoke tested each year | Illicit Connections, groundwater infiltration | Property Owners, City Public Works Director | City Public Works Director
| 6c. |  |  | X | X | X | X | Enforce removal of illicit connections detected | 100% of illicit connections removed | Illicit Connections | Property Owners | City Public Works Director
| 6d. |  |  |  | X | X | X | Develop Capital Improvement Plan for repairing/replacing areas of Storm Drainage system with large amounts of groundwater infiltration | Development of Capital Improvement Plan with budget and schedule for storm drain piping replacement | Groundwater Infiltration | City Engineer, Public Works Director, City Council | City Public Works Director
Illicit Discharge Detection and Elimination | 7a. | Maintenance Logs and Visual Observations |  | X |  |  |  | Develop a storm system maintenance log to document the location and observations made during storm drain maintenance, including excessive debris, suspicious discharges, odors, dry-weather flow, structural problems, and others. | Maintenance form developed | Illicit Discharges | Public Works Employees | City Public Works Director
| 7b. |  |  | X | X | X | X | Train Public Works employees in the use of the maintenance log form & oversee use | 100% of applicable Public Works employees trained and using form | Illicit Discharges | Public Works Employees | City Public Works Director and Public Works Employees
| 7c. |  |  | X | X | X | X | Track the locations of illicit discharges to determine areas of concern to be targeted for outreach and additional monitoring / maintenance | Areas of concern identified and additional outreach, monitoring and maintenance conducted | Illicit Discharges | Areas of concern to be identified | City Public Works Director and Public Works Employees
| 7d. |  |  |  | X | X | X | Perform additional outreach, monitoring, and maintenance as necessary | Additional outreach, monitoring, and maintenance performed to 100 % of identified areas of concern | Illicit Discharges | Areas of concern to be identified | City Public Works Director and Public Works Employees
Construction Site Storm Water Runoff Control | 1a. | Erosion Control Ordinance | X |  |  |  |  | Complete Draft Storm Water Quality Management and Discharge Control ordinance | Draft Ordinance finalized | Sediment and priority pollutants | City Attorney, Public Works Director, City Engineer | City Public Works Director
| 1b. |  | X |  |  |  |  | City Attorney and City Engineer to review storm water ordinance | Storm water ordinance reviewed and revised | Sediment and priority pollutants | City Attorney, Public Works Director, City Engineer | City Attorney, Public Works Director, City Engineer
| 1c. |  |  | X |  |  |  | Present ordinance to City Council | Storm water ordinance adopted | Sediment and priority pollutants | City Council | City Public Works Director
| 1d. |  |  | X | X |  |  | Include information on the storm water ordinance in public service announcements | Information on the storm water ordinance included in at least 1 public service announcement | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 1e. |  |  | X | X | X | X | Oversee implementation and enforcement of ordinance | Enforce 100 % of observed illicit discharges | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
Construction Site Storm Water Runoff Control | 2a. | Best Management Practices Manual |  | X |  |  |  | Complete Draft Best Management Practices Manual | Draft BMP Manual | Sediment and priority pollutants | City Attorney, Public Works Director, City Engineer | City Public Works Director
| 2b. |  |  | X |  |  |  | City Attorney and City Engineer to review Draft BMP Manual | BMP Manual reviewed and revised | Sediment and priority pollutants | City Attorney, Public Works Director, City Engineer | City Attorney, Public Works Director, City Engineer
| 2c. |  |  |  | X |  |  | Present BMP Manual to City Council for adoption | BMP Manual adopted | Sediment and priority pollutants | City Council | City Public Works Director
| 2d. |  |  |  | X |  |  | Include information on the BMP Manual in public service announcements | Information on the BMP Manual included in at least 1 public service announcement | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 2e. |  |  |  | X | X | X | Oversee implementation of BMP Manual | Enforce 100 % of implementation of BMP Manual | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 3a. | Storm Water Hotline | X |  |  |  |  | Establish Storm Water Hotline | Dedicated phone number established for use as storm water hotline | Sediment, hydrocarbons and other priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 3b. |  | X |  |  |  |  | Establish Tracking Sheet for use by Hotline Operator to track complaint and action taken | Tracking sheet | Sediment, hydrocarbons and other priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 3c. |  |  | X | X | X | X | Advertise the Storm Water Hotline number on all educational pamphlets, posters, and storm water web site developed with the North Coast Storm Water Coalition | 25 % Compliance each fiscal year for 100 % compliance by end of permit term | Sediment, hydrocarbons and other priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 3d. |  |  | X | X | X | X | Review the types of complaints to determine areas of concern to be targeted for outreach and additional monitoring | Areas of concern identified and additional outreach & monitoring conducted | Sediment, hydrocarbons and other priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 3e. |  |  |  | X | X | X | Perform additional outreach, monitoring, and maintenance as necessary | Additional outreach & monitoring performed on 100 % of identified areas of concern | Sediment, hydrocarbons and other priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 4a. | Construction Site Inspections | X | X | X | X | X | Building Inspection staff to continue inspecting construction sites to ensure proper erosion and sediment controls | Inspect 100 % of construction sites | Sediment | Contractors | Public Works Director & Building Inspectors
| 4b. |  |  | X | X |  |  | Public Works to develop construction site inspection procedures, including checklists, educational materials, scheduling for pre-storm and post-storm inspections, and enforcement. | Inspect, document, and enforce 100 % of construction sites | Sediment | Contractors | City Public Works Director
Construction Site Storm Water Runoff Control | 5a. | Construction Permit Plan Review & Tracking | X | X | X | X | X | Building Permit staff to continue review of Building & Grading Permits for construction to ensure proper erosion and sediment controls | Review 100% of Building & Grading Permit applications for sediment and erosion control plans | Sediment | Developers & Contractors | Public Works Director & Building Dept. permit review employees
| 5b. |  |  | X | X |  |  | Building Department to develop construction & grading permit review procedures, including checklists, & educational materials | Review, document, and enforce 100 % of permit requirements | Sediment | Developers & Contractors | City Public Works Director
| 5c. |  |  |  | X | X | X | Track the proportion of erosion control plans submitted that meet the city's new standards for erosion control | Evaluate the results and determine if additional education and outreach to developers and contractors is needed; Conduct additional outreach as necessary. | Sediment | Developers, Engineers, and Contractors | City Public Works Director
| 6 | Contractor Education |  | X | X | X | X | Develop and distribute outreach materials for developers and contractors such as a flowchart describing the Erosion Control Plan requirements. | Outreach materials distributed to 100 % of developers / contractors during pre-construction meetings | Sediment | Developers, Contractors | City Public Works Director
| 7a. | City Staff Education |  | X | X | X | X | Provide in-house training during staff review committee meetings regarding new erosion control ordinance requirements and BMP Manual to appropriate Public Works, Building, and Planning Department staff involved with plan review, approval, and construction site inspections. | 100 % of appropriate staff received training | Sediment | Staff to be identified | City Public Works Director
| 7b. |  |  | X | X | X | X | Coordinate with local agencies on potential joint training opportunities for City Staff | 100 % of appropriate staff receive training by the end of the permit term | Sediment | Staff to be identified | City Public Works Director
Post-Construction Storm Water Management in New Development and Redevelopment | 1a. | Erosion Control Ordinance | X |  |  |  |  | Complete Draft Storm Water Quality Management and Discharge Control ordinance | Draft Ordinance finalized | Sediment and priority pollutants | City Attorney, Public Works Director, City Engineer | City Public Works Director
| 1b. |  | X |  |  |  |  | City Attorney and City Engineer to review storm water ordinance | Storm water ordinance reviewed and revised | Sediment and priority pollutants | City Attorney, Public Works Director, City Engineer | City Attorney, Public Works Director, City Engineer
| 1c. |  |  | X |  |  |  | Present ordinance to City Council | Storm water ordinance adopted | Sediment and priority pollutants | City Council | City Public Works Director
| 1d. |  |  | X | X |  |  | Include information on the storm water ordinance in public service announcements | Information on the storm water ordinance included in at least 1 public service announcement | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 1e. |  |  | X | X | X | X | Oversee implementation and enforcement of ordinance | Enforce 100 % of observed illicit discharges | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
Post-Construction Storm Water Management in New Development and Redevelopment | 2a. | Best Management Practices Manual |  | X |  |  |  | Complete Draft Best Management Practices Manual | Draft BMP Manual | Sediment and priority pollutants | City Attorney, Public Works Director, City Engineer | City Public Works Director
| 2b. |  |  | X |  |  |  | City Attorney and City Engineer to review Draft BMP Manual | BMP Manual reviewed and revised | Sediment and priority pollutants | City Attorney, Public Works Director, City Engineer | City Attorney, Public Works Director, City Engineer
| 2c. |  |  |  | X |  |  | Present BMP Manual to City Council for adoption | BMP Manual adopted | Sediment and priority pollutants | City Council | City Public Works Director
| 2d. |  |  |  | X |  |  | Include information on the BMP Manual in public service announcements | Information on the BMP Manual included in at least 1 public service announcement | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 2e. |  |  |  | X | X | X | Oversee implementation of BMP Manual | Enforce 100 % of implementation of BMP Manual | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 3a. | BMP Inspections and Maintenance |  | X |  |  |  | Coordinate with City's Pre-Treatment Coordinator to develop a program to inspect and enforce the ordinance requirements for property owners of existing and new developments to monitor and maintain source and treatment control BMPs | All new source and treatment control BMPs are maintained at least once a year or as specified by the designer or manufacturer of the BMP | Sediment and priority pollutants | Pre-Treatment Coordinator & City Public Works Director | Pre-Treatment Coordinator & City Public Works Director
| 3b. |  |  |  | X | X | X | Inspect BMPs on existing and new developments & enforce ordinance requirements | 100 % Inspection of existing and new structural BMPs | Sediment and priority pollutants | Pre-Treatment Coordinator & City Public Works Director | Pre-Treatment Coordinator & City Public Works Director
| 3c. |  |  |  | X | X | X | Review data from BMP inspections to determine problem areas and areas where additional education, inspection and enforcement required | Review of 100 % of inspection forms | Sediment and priority pollutants | Pre-Treatment Coordinator & City Public Works Director | City Public Works Director
| 3d. |  |  |  |  | X |  | Develop a post-construction BMP maintenance program for future post-construction BMPs on City owned properties | Program developed and implemented that identifies post-construction BMPs on City owned properties and schedules for operation and maintenance. | Sediment and priority pollutants | Public Works | City Public Works Director
| 4a. | Watercourse Protection |  | X | X | X | X | Respond to complaints received on Storm Water Hotline & through routine construction inspection or maintenance and enforce watercourse provisions of storm water ordinance | 100 % response to complaints on watercourse impacts | Sediment and priority pollutants | Public Works | City Public Works Director
| 4b. |  |  | X | X | X | X | Review the types of complaints to determine areas of concern to be targeted for outreach and additional monitoring | Areas of concern identified and additional outreach & monitoring conducted | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 4c. |  |  |  | X | X | X | Perform additional outreach & monitoring as necessary | Additional outreach & monitoring performed on 100 % of identified areas of concern | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 5a. | Contractor Education |  |  | X | X | X | Develop and distribute outreach materials for developers and contractors on structural BMP operation & maintenance requirements. | Outreach materials distributed to 100 % of developers / contractors during pre-construction meetings | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
| 5b. |  |  |  |  | X | X | Track the inspection & maintenance of structural BMP | Evaluate the results and determine if additional education and outreach to developers and contractors is needed; Conduct additional outreach as necessary. | Sediment and priority pollutants | Developers, Contractors & General Public | City Public Works Director
Post-Construction Storm Water Management in New Development and Redevelopment | 6a. | City Staff Education |  | X | X | X | X | Provide in-house training during staff review committee meetings regarding new erosion control ordinance requirements and BMP Manual to appropriate Public Works, Building, and Planning Department staff involved with plan review, approval, and construction site inspections. | 100 % of appropriate staff received training | Sediment and priority pollutants | Staff to be identified | City Public Works Director
| 6b. |  |  | X | X | X | X | Coordinate with local agencies on potential joint training opportunities for City Staff | 100 % of appropriate staff receive training by the end of the permit term | Sediment and priority pollutants | Staff to be identified | City Public Works Director
Pollution Prevention/ Good Housekeeping for Municipal Operations | 1a. | Operation & Maintenance Manual |  | X | X |  |  | Complete Draft Operation & Maintenance Manual | Draft Manual finalized | Sediment and priority pollutants | City Attorney, Public Works Director, City Engineer | City Public Works Director
| 1b. |  |  |  | X |  |  | City Attorney and City Engineer to review Operation & Maintenance Manual | Operation & Maintenance Manual reviewed and revised | Sediment and priority pollutants | City Attorney, Public Works Director, City Engineer | City Attorney, Public Works Director, City Engineer
| 1c. |  |  |  | X |  |  | Present O&M Manual to City Council | Operation & Maintenance Manual adopted | Sediment and priority pollutants | City Council | City Public Works Director
| 1d. |  |  |  | X | X | X | Implement O & M Manual in all applicable City Department & provide training to all applicable City Staff | 100 % Implement of O & M Manual at all City Departments & 100 % of staff trained in its contents | Sediment and priority pollutants | Public Works Employees | City Public Works Director & Public Work Department Supervisors
| 1e. |  |  |  | X | X | X | Conduct annual review of City practices to ensure conformance to O&M Manual. Identify areas of additional education requirements and provide to City employees | 100 % annual review of all applicable City Departments for compliance with O&M Manual | Sediment and priority pollutants | Public Works Employees | City Public Works Director & Public Work Department Supervisors
| 2a. | Street Sweeping | X | X | X | X | X | Continue street sweeping operations | 100 % of City Streets swept weekly | Sediment and trash | Public Works Employees | City Public Works Director
| 2b. |  |  | X | X | X | X | Identify areas where more frequent cleaning of streets is necessary. | Areas of concern identified | Sediment and trash | Public Works | City Public Works Director
| 2c. |  |  | X | X | X | X | Target identified areas of concern for more frequent cleaning and educational outreach as appropriate | More frequent cleaning of the areas identified | Sediment and trash | Public Works | City Public Works Director
| 3a. | Storm Drain System Cleaning |  | X |  |  |  | Develop a maintenance form to record storm drain maintenance activities, including observations of illicit discharges. | Maintenance form developed | Sediment and trash | Public Works | City Public Works Director
| 3b. |  |  | X |  |  |  | Provide in-house training related to use of the maintenance form to Public Works staff | 100 % of appropriate Public Works staff receive training | Sediment and trash | Public Works | City Public Works Director
| 3c. |  |  | X | X | X | X | Use storm drain maintenance log to record storm drain system maintenance. | 100 % of maintenance tracked | Sediment and trash | Public Works | City Public Works Director
| 3d. |  |  |  | X | X | X | Identify areas where more frequent cleaning is necessary | Areas identified and maintained more frequently | Sediment and trash | Public Works | City Public Works Director
Pollution Prevention/ Good Housekeeping for Municipal Operations | 4a. | Integrated Pesticide, Herbicide, and Fertilizer Management Plan |  |  | X |  |  | Review current landscape policies, including an inventory of pesticides, herbicides, and fertilizers used. | 100 % of pesticides / herbicides inventoried; Evaluation of current procedures completed | Pesticides / Herbicides | Public Works Employees | City Public Works Director
| 4b. |  |  |  | X | X |  | Prepare Management Plan outlining alternative methods to reduce use of pesticides and herbicides & establish application rates and methods | Preparation of Integrated Pesticide, Herbicide, & Fertilizer Management Plan | Pesticides / Herbicides | Public Works Employees | City Public Works Director
| 4c. |  |  |  |  | X |  | Train Public Works employees in the contents of Management Plan | 100 % of applicable Public Works staff receive training | Pesticides / Herbicides | Public Works Employees | City Public Works Director
| 4d. |  |  |  |  | X | X | Implement of Management Plan on all City properties | Reduction in the volume of pesticides and herbicides used | Pesticides / Herbicides | Public Works Employees | City Public Works Director
Abbreviations:
BMP = Best Management Practice | [7 empty] | O&M = Operation and Maintenance Manual
CUPA = Certified Unified Program Agency | [7 empty] | RCAA = Redwood Community Action Agency
DEH = Humboldt County Division of Environmental Health | [7 empty] | SWMP = Storm Water Management Plan

## Table 3
Minimum Control Measure | BMP # | Activity/Best Management Practices | [5 empty] | Implementation Plan | Approx. No. of Staff Hours or Material Cost per Fiscal Year | Units | Unit Cost per Fiscal Year | Total Cost per Fiscal Year
|  |  | FY 05/06 | FY 06/07 | FY 07/08 | FY 08/09 | FY 09/10 |  |  |  |  | FY 05/06 | FY 06/07 | FY 07/08 | FY 08/09 | FY 09/10
Public Education and Outreach | 1a. | North Coast Storm Water Coalition | X |  |  |  |  | Finalize six posters educating public on storm water impacts of pet wastes, leaking oil, hazardous waste disposal, car washing, cigarette butts, and fertilizers and pesticides | 100 | Staff Hours | 120 | 12000 | 0 | 0 | 0 | 0
| 1b. |  |  | X | X | X | X | Distribute posters to school, city agencies, and general public | 500 | Poster Printing/Distribution | 10 | 0 | 5000 | 5000 | 5000 | 5000
| 1c. |  | X | X | X | X | X | Develop storm water web site | 120 | Staff Hours | 50 | 6000 | 6000 | 6000 | 6000 | 6000
| 1d. |  |  | X |  |  |  | Identify additional public education and outreach task to benefit all members of Coalition | 80 | Staff Hours | 120 | 0 | 9600 | 0 | 0 | 0
| 2a. | Reaches To Beaches | X |  |  |  |  | Survey all schools in City for interest in participation in program | 80 | Staff Hours | 50 | 4000 | 0 | 0 | 0 | 0
| 2b. |  |  | X |  |  |  | Coordinate with RCAA on identifying staff to implement program | 80 | Staff Hours | 50 | 0 | 4000 | 0 | 0 | 0
| 2c. |  |  | X | X | X | X | Implement Program at local schools | 80 | Staff Hours | 50 | 0 | 4000 | 4000 | 4000 | 4000
| 3a. | Educational Component of Existing Commercial and Industrial Inspections | X | X | X | X | X | Coordinate with the City's Pre-Treatment Coordinator, County CUPA Program, and County Used Oil Program Coordinator to ensure that all industrial and applicable commercial businesses within the City receive storm water educational materials at least once during the permit term. | 100 | Staff Hours | 120 | 12000 | 12000 | 12000 | 12000 | 12000
| 4 | Pet Waste Signs | X | X | X | X | X | Identify appropriate locations and install pet waste kiosks with signage and bag dispenser at appropriate parks and other public recreational areas within the City encouraging the public to pick up after their pet. | 1 | Identification of sites and installation of kiosks | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
| 5a. | Storm Drain Marking | X | X | X | X | X | Coordinate with County Used Oil Program, Reaches to Beaches students, and City Pre-Treatment Coordinator on storm drain stenciling opportunities | 16 | Staff Hours | 120 | 1920 | 1920 | 1920 | 1920 | 1920
| 5b. |  |  | X | X | X | X | Amend storm drain design standards to require developers to install cast iron embossed covers with a no dumping message on all new storm drains | 40 | Staff Hours | 120 | 0 | 4800 | 4800 | 4800 | 4800
Public Education and Outreach | 6a. | Storm Water Hotline | X |  |  |  |  | Establish Storm Water Hotline | 40 | Staff Hours | 120 | 4800 | 0 | 0 | 0 | 0
| 6b. |  | X |  |  |  |  | Establish Tracking Sheet for use by Hotline Operator to track complaint and action taken | 20 | Staff Hours | 120 | 2400 | 0 | 0 | 0 | 0
| 6c. |  |  | X | X | X | X | Advertise the Storm Water Hotline number on all educational pamphlets, posters, and storm water web site developed with the North Coast Storm Water Coalition | 1000 | Costs for amending & printing pamphlets | 10 | 0 | 10000 | 10000 | 10000 | 10000
| 7a. | Educational Outreach to Public | X | X | X | X | X | Distribute storm water educational materials at appropriate activities held at the Adorni Center | 16 | Staff Hours | 50 | 800 | 800 | 800 | 800 | 800
| 7b. |  |  | X | X | X | X | Provide free educational materials at City Hall | 1000 | Pamphlet costs | 5 | 0 | 5000 | 5000 | 5000 | 5000
| 7c. |  | X | X | X | X | X | Develop and submit storm water program related public service announcements to local radio station or newspaper. | 1 | Ad development & running | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
| 7d. | Community Spring Cleanup Day | X | X | X | X | X | Advertise the Community Spring Cleanup Day and hold event to clean up City Parks, neighborhoods, waterfront and streams | 1 | Ad development & running | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
| 7e. | Construction Pamphlets |  | X |  |  |  | Develop a series of pamphlets describing City's new Storm Water Ordinance and BMP Manual and permitting requirements | 40 | Staff Hours | 120 | 0 | 4800 | 0 | 0 | 0
| 7f. |  |  |  | X | X | X | Distribute pamphlets during pre-construction meetings and construction site inspections | 1000 | Pamphlet costs | 5 | 0 | 0 | 5000 | 5000 | 5000
| 1a. | Humboldt Bay First Flush Study | X | X | X | X | X | Coordinate with City of Arcata, Humboldt County, and RCAA to advertise First Flush Study and seek volunteers | 40 | Staff Hours | 120 | 4800 | 4800 | 4800 | 4800 | 4800
| 1b. |  | X | X | X | X | X | Identify and train at least 20 volunteers to perform first flush sampling | 24 | Staff Hours | 50 | 1200 | 1200 | 1200 | 1200 | 1200
| 1c. |  | X | X | X | X | X | Perform First Flush Sampling Annually | 40 | Staff Hours | 120 | 4800 | 4800 | 4800 | 4800 | 4800
| 1d. |  |  | X | X | X | X | Evaluate the first flush sampling results to develop future SWMP policy, including outreach BMPs as appropriate. | 24 | Staff Hours | 120 | 0 | 2880 | 2880 | 2880 | 2880
| 2a. | Reaches To Beaches | X |  |  |  |  | Survey all schools in City for interest in participation in program | Funded Under Public Ed. MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 2b. |  |  | X |  |  |  | Coordinate with RCAA on identifying staff to implement program | Funded Under Public Ed. MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 2c. |  |  | X | X | X | X | Implement Program at local schools | Funded Under Public Ed. MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
Illicit Discharge Detection and Elimination | 3 | Community Spring Cleanup Day | X | X | X | X | X | Hold the Community Spring Cleanup Day to get public involved in cleaning up City Parks, neighborhoods, waterfront and streams | 80 | Staff Hours | 120 | 9600 | 9600 | 9600 | 9600 | 9600
| 4a. | Storm Drain Stenciling | X | X | X | X | X | Coordinate with County Used Oil Program, Reaches to Beaches students, and City Pre-Treatment Coordinator on storm drain stenciling opportunities | 40 | Staff Hours | 120 | 4800 | 4800 | 4800 | 4800 | 4800
| 4b. |  |  | X | X | X | X | Hold at least one storm drain marking event with the public each year | 1 | Paint, stencils, & coordination | 2000 | 0 | 2000 | 2000 | 2000 | 2000
| 1a. | Identifying Illicit Discharges |  | X | X | X | X | Coordinate with City's Pre-Treatment Coordinator on inspections of permitted industrial dischargers and complaint response | 24 | Staff Hours | 120 | 0 | 2880 | 2880 | 2880 | 2880
| 1b. |  |  | X | X | X | X | Track complaints received through Public Works Department. Maintain records of follow-up activities to show that discharges are adequately addressed. | 80 | Staff Hours | 50 | 0 | 4000 | 4000 | 4000 | 4000
| 1c. |  | X | X | X | X | X | Enforce water waste prohibition. | 120 | Staff Hours | 50 | 6000 | 6000 | 6000 | 6000 | 6000
| 2a. | Storm Water Hotline | X |  |  |  |  | Establish Storm Water Hotline | Funded Under Public Ed. MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 2b. |  | X |  |  |  |  | Establish Tracking Sheet for use by Hotline Operator to track complaint and action taken | Funded Under Public Ed. MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 2c. |  |  | X | X | X | X | Forward complaints of illicit discharges to City Pre-Treatment Coordinator, County Environmental Health or other appropriate personnel | 80 | Staff Hours | 50 | 0 | 4000 | 4000 | 4000 | 4000
| 2d. |  |  | X | X | X | X | Review complaint logs to identify areas or target audience where additional inspections or education is required | 40 | Staff Hours | 120 | 0 | 4800 | 4800 | 4800 | 4800
| 3a. | Storm Water GIS | X |  |  |  |  | Complete the City's Storm Water GIS web site | 120 | Staff Hours | 80 | 9600 | 0 | 0 | 0 | 0
| 3b. |  |  | X |  |  |  | Advertise the existence of the GIS web site to the public and other agencies through GIS user's group meetings and providing link on Storm Water web site. | 40 | Staff Hours | 80 | 0 | 3200 | 0 | 0 | 0
Illicit Discharge Detection and Elimination | 4a. | Storm Water Ordinance | X |  |  |  |  | Complete Draft Storm Water Quality Management and Discharge Control ordinance | 40 | Staff Hours | 120 | 4800 | 0 | 0 | 0 | 0
| 4b. |  | X |  |  |  |  | City Attorney and City Engineer to review storm water ordinance | 120 | Staff Hours | 120 | 14400 | 0 | 0 | 0 | 0
| 4c. |  |  | X |  |  |  | Present ordinance to City Council | 24 | Staff Hours | 120 | 0 | 2880 | 0 | 0 | 0
| 4d |  |  | X |  |  |  | Public Works to conduct in-house training related to ordinance enforcement | 120 | Staff Hours | 50 | 0 | 6000 | 0 | 0 | 0
| 4e |  |  | X | X |  |  | Include information on the storm water ordinance in public service announcements | 1 | Ad development & running | 2000 | 0 | 2000 | 2000 | 0 | 0
| 4f |  |  | X | X | X | X | Oversee implementation and enforcement of ordinance | 40 | Staff Hours | 120 | 0 | 4800 | 4800 | 4800 | 4800
| 5a. | Commercial & Industrial Inspections |  | X |  |  |  | Coordinate with City Pre-Treatment Coordinator, County Division of Environmental Health, and County CUPA to develop form to track illicit connections, spills, and discharges | 80 | Staff Hours | 120 | 0 | 9600 | 0 | 0 | 0
| 5b. |  |  | X | X | X | X | Track the locations of illicit discharges to determine areas of concern to be targeted for outreach and additional monitoring / maintenance | 80 | Staff Hours | 50 | 0 | 4000 | 4000 | 4000 | 4000
| 5c. |  |  | X | X | X | X | Obtain and evaluate results of commercial / industrial inspections performed by the Cit Pre-Treatment Coordinator, County DEH, and County CUPA | 40 | Staff Hours | 120 | 0 | 4800 | 4800 | 4800 | 4800
| 5d. |  |  |  | X | X | X | Perform additional outreach, monitoring, and maintenance as necessary | 40 | Staff Hours | 50 | 0 | 0 | 2000 | 2000 | 2000
| 6a. | Smoke Testing & Illicit Connection Detection & Elimination |  | X |  |  |  | Develop operations plan with schedule and tracking system for performing smoke testing of the storm drain system | 160 | Staff Hours | 80 | 0 | 12800 | 0 | 0 | 0
| 6b. |  |  | X | X | X | X | Perform Smoke Testing of the System | 5000 | Feet of Sewer Tested | 2 | 0 | 10000 | 10000 | 10000 | 10000
| 6c. |  |  | X | X | X | X | Enforce removal of illicit connections detected | 80 | Staff Hours | 50 | 0 | 4000 | 4000 | 4000 | 4000
| 6d. |  |  |  | X | X | X | Develop Capital Improvement Plan for repairing/replacing areas of Storm Drainage system with large amounts of groundwater infiltration | 160 | Staff Hours | 120 | 0 | 0 | 19200 | 19200 | 19200
Construction Site Storm Water Runoff Control | 7a. | Maintenance Logs and Visual Observations |  | X |  |  |  | Develop a storm system maintenance log to document the location and observations made during storm drain maintenance, including excessive debris, suspicious discharges, odors, dry-weather flow, structural problems, and others. | 80 | Staff Hours | 50 | 0 | 4000 | 0 | 0 | 0
| 7b. |  |  | X | X | X | X | Train Public Works employees in the use of the maintenance log form & oversee use | 120 | Staff Hours | 50 | 0 | 6000 | 6000 | 6000 | 6000
| 7c. |  |  | X | X | X | X | Track the locations of illicit discharges to determine areas of concern to be targeted for outreach and additional monitoring / maintenance | 120 | Staff Hours | 50 | 0 | 6000 | 6000 | 6000 | 6000
| 7d. |  |  |  | X | X | X | Perform additional outreach, monitoring, and maintenance as necessary | 80 | Staff Hours | 120 | 0 | 0 | 9600 | 9600 | 9600
| 1a. | Erosion Control Ordinance | X |  |  |  |  | Complete Draft Storm Water Quality Management and Discharge Control ordinance | Funded Under Illicit Discharge MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 1b. |  | X |  |  |  |  | City Attorney and City Engineer to review storm water ordinance | Funded Under Illicit Discharge MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 1c. |  |  | X |  |  |  | Present ordinance to City Council | Funded Under Illicit Discharge MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 1d. |  |  | X | X |  |  | Include information on the storm water ordinance in public service announcements | Funded Under Illicit Discharge MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 1e. |  |  | X | X | X | X | Oversee implementation and enforcement of ordinance | Funded Under Illicit Discharge MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 2a. | Best Management Practices Manual |  | X |  |  |  | Complete Draft Best Management Practices Manual | 320 | Staff Hours | 120 | 0 | 38400 | 0 | 0 | 0
| 2b. |  |  | X |  |  |  | City Attorney and City Engineer to review Draft BMP Manual | 80 | Staff Hours | 120 | 0 | 9600 | 0 | 0 | 0
| 2c. |  |  |  | X |  |  | Present BMP Manual to City Council for adoption | 40 | Staff Hours | 120 | 0 | 0 | 4800 | 0 | 0
| 2d. |  |  |  | X |  |  | Include information on the BMP Manual in public service announcements | 1 | Ad development & running | 2000 | 0 | 0 | 2000 | 0 | 0
| 2e. |  |  |  | X | X | X | Oversee implementation of BMP Manual | 40 | Staff Hours | 120 | 0 | 0 | 4800 | 4800 | 4800
Construction Site Storm Water Runoff Control | 3a. | Storm Water Hotline | X |  |  |  |  | Establish Storm Water Hotline | Funded Under Public Ed. MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 3b. |  | X |  |  |  |  | Establish Tracking Sheet for use by Hotline Operator to track complaint and action taken | Funded Under Public Ed. MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 3c. |  |  | X | X | X | X | Advertise the Storm Water Hotline number on all educational pamphlets, posters, and storm water web site developed with the North Coast Storm Water Coalition | Funded Under Public Ed. MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 3d. |  |  | X | X | X | X | Review the types of complaints to determine areas of concern to be targeted for outreach and additional monitoring | 24 | Staff Hours | 120 | 0 | 2880 | 2880 | 2880 | 2880
| 3e. |  |  |  | X | X | X | Perform additional outreach, monitoring, and maintenance as necessary | 40 | Staff Hours | 50 | 0 | 0 | 2000 | 2000 | 2000
| 4a. | Construction Site Inspections | X | X | X | X | X | Building Inspection staff to continue inspecting construction sites to ensure proper erosion and sediment controls | 520 | Additional Staff Hours devoted to sediment/erosion control | 50 | 26000 | 26000 | 26000 | 26000 | 26000
| 4b. |  |  | X | X |  |  | Public Works to develop construction site inspection procedures, including checklists, educational materials, scheduling for pre-storm and post-storm inspections, and enforcement. | 160 | Staff Hours | 50 | 0 | 8000 | 8000 | 0 | 0
| 5a. | Construction Permit Plan Review & Tracking | X | X | X | X | X | Building Permit staff to continue review of Building & Grading Permits for construction to ensure proper erosion and sediment controls | 200 | Additional Staff Hours devoted to sediment/erosion control | 80 | 16000 | 16000 | 16000 | 16000 | 16000
| 5b. |  |  | X | X |  |  | Building Department to develop construction & grading permit review procedures, including checklists, & educational materials | 120 | Staff Hours | 80 | 0 | 9600 | 9600 | 0 | 0
| 5c. |  |  |  | X | X | X | Track the proportion of erosion control plans submitted that meet the city's new standards for erosion control | 100 | Staff Hours | 50 | 0 | 0 | 5000 | 5000 | 5000
| 6 | Contractor Education |  | X | X | X | X | Develop and distribute outreach materials for developers and contractors such as a flowchart describing the Erosion Control Plan requirements. | 120 | Staff Hours | 120 | 0 | 14400 | 14400 | 14400 | 14400
| 7a. | City Staff Education |  | X | X | X | X | Provide in-house training during staff review committee meetings regarding new erosion control ordinance requirements and BMP Manual to appropriate Public Works, Building, and Planning Department staff involved with plan review, approval, and construction | 160 | Staff Hours | 80 | 0 | 12800 | 12800 | 12800 | 12800
| 7b. |  |  | X | X | X | X | Coordinate with local agencies on potential joint training opportunities for City Staff | 16 | Staff Hours | 120 | 0 | 1920 | 1920 | 1920 | 1920
Post-Construction Storm Water Management in New Development and Redevelopment | 1a. | Erosion Control Ordinance | X |  |  |  |  | Complete Draft Storm Water Quality Management and Discharge Control ordinance | Funded Under Illicit Discharge MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 1b. |  | X |  |  |  |  | City Attorney and City Engineer to review storm water ordinance | Funded Under Illicit Discharge MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 1c. |  |  | X |  |  |  | Present ordinance to City Council | Funded Under Illicit Discharge MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 1d. |  |  | X | X |  |  | Include information on the storm water ordinance in public service announcements | Funded Under Illicit Discharge MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 1e. |  |  | X | X | X | X | Oversee implementation and enforcement of ordinance | Funded Under Illicit Discharge MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 2a. | Best Management Practices Manual |  | X |  |  |  | Complete Draft Best Management Practices Manual | Funded Under Construction MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 2b. |  |  | X |  |  |  | City Attorney and City Engineer to review Draft BMP Manual | Funded Under Construction MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 2c. |  |  |  | X |  |  | Present BMP Manual to City Council for adoption | Funded Under Construction MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 2d. |  |  |  | X |  |  | Include information on the BMP Manual in public service announcements | Funded Under Construction MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 2e. |  |  |  | X | X | X | Oversee implementation of BMP Manual | Funded Under Construction MCM | Staff Hours | 0 | 0 | 0 | 0 | 0 | 0
| 3a. | BMP Inspections and Maintenance |  | X |  |  |  | Coordinate with City's Pre-Treatment Coordinator to develop a program to inspect and enforce the ordinance requirements for property owners of existing and new developments to monitor and maintain source and treatment control BMPs | 80 | Staff Hours | 120 | 0 | 9600 | 0 | 0 | 0
| 3b. |  |  |  | X | X | X | Inspect BMPs on existing and new developments & enforce ordinance requirements | 120 | Staff Hours | 80 | 0 | 0 | 9600 | 9600 | 9600
| 3c. |  |  |  | X | X | X | Review data from BMP inspections to determine problem areas and areas where additional education, inspection and enforcement required | 24 | Staff Hours | 120 | 0 | 0 | 2880 | 2880 | 2880
| 3d. |  |  |  |  | X |  | Develop a post-construction BMP maintenance program for future post-construction BMPs on City owned properties | 40 | Staff Hours | 120 | 0 | 0 | 0 | 4800 | 0
Post-Construction Storm Water Management in New Development and Redevelopment | 4a. | Watercourse Protection |  | X | X | X | X | Respond to complaints received on Storm Water Hotline & through routine construction inspection or maintenance and enforce watercourse provisions of storm water ordinance | 40 | Staff Hours | 80 | 0 | 3200 | 3200 | 3200 | 3200
| 4b. |  |  | X | X | X | X | Review the types of complaints to determine areas of concern to be targeted for outreach and additional monitoring | 40 | Staff Hours | 120 | 0 | 4800 | 4800 | 4800 | 4800
| 4c. |  |  |  | X | X | X | Perform additional outreach & monitoring as necessary | 40 | Staff Hours | 120 | 0 | 0 | 4800 | 4800 | 4800
| 5a. | Contractor Education |  |  | X | X | X | Develop and distribute outreach materials for developers and contractors on structural BMP operation & maintenance requirements. | 120 | Staff Hours | 120 | 0 | 0 | 14400 | 14400 | 14400
| 5b. |  |  |  |  | X | X | Track the inspection & maintenance of structural BMP | 24 | Staff Hours | 120 | 0 | 0 | 0 | 2880 | 2880
| 6a. | City Staff Education |  | X | X | X | X | Provide in-house training during staff review committee meetings regarding new erosion control ordinance requirements and BMP Manual to appropriate Public Works, Building, and Planning Department staff involved with plan review, approval, and construction | 80 | Staff Hours | 80 | 0 | 6400 | 6400 | 6400 | 6400
| 6b. |  |  | X | X | X | X | Coordinate with local agencies on potential joint training opportunities for City Staff | 24 | Staff Hours | 120 | 0 | 2880 | 2880 | 2880 | 2880
Pollution Prevention/ Good Housekeeping for Municipal Operations | 1a. | Operation & Maintenance Manual |  | X | X |  |  | Complete Draft Operation & Maintenance Manual | 200 | Staff Hours | 80 | 0 | 16000 | 16000 | 0 | 0
| 1b. |  |  |  | X |  |  | City Attorney and City Engineer to review Operation & Maintenance Manual | 80 | Staff Hours | 120 | 0 | 0 | 9600 | 0 | 0
| 1c. |  |  |  | X |  |  | Present O&M Manual to City Council | 24 | Staff Hours | 120 | 0 | 0 | 2880 | 0 | 0
| 1d. |  |  |  | X | X | X | Implement O & M Manual in all applicable City Department & provide training to all applicable City Staff | 160 | Staff Hours | 80 | 0 | 0 | 12800 | 12800 | 12800
| 1e. |  |  |  | X | X | X | Conduct annual review of City practices to ensure conformance to O&M Manual. Identify areas of additional education requirements and provide to City employees | 80 | Staff Hours | 120 | 0 | 0 | 9600 | 9600 | 9600
| 2a. | Street Sweeping | X | X | X | X | X | Continue street sweeping operations | 1040 | Staff & Equip Costs | 150 | 156000 | 156000 | 156000 | 156000 | 156000
| 2b. |  |  | X | X | X | X | Identify areas where more frequent cleaning of streets is necessary. | 80 | Staff Hours | 120 | 0 | 9600 | 9600 | 9600 | 9600
| 2c. |  |  | X | X | X | X | Target identified areas of concern for more frequent cleaning and educational outreach as appropriate | 80 | Staff Hours | 50 | 0 | 4000 | 4000 | 4000 | 4000
Pollution Prevention/ Good Housekeeping for Municipal Operations | 3a. | Storm Drain System Cleaning |  | X |  |  |  | Develop a maintenance form to record storm drain maintenance activities, including observations of illicit discharges. | 80 | Staff Hours | 80 | 0 | 6400 | 0 | 0 | 0
| 3b. |  |  | X |  |  |  | Provide in-house training related to use of the maintenance form to Public Works staff | 120 | Staff Hours | 80 | 0 | 9600 | 0 | 0 | 0
| 3c. |  |  | X | X | X | X | Use storm drain maintenance log to record storm drain system maintenance. | 140 | Staff Hours | 50 | 0 | 7000 | 7000 | 7000 | 7000
| 3d. |  |  |  | X | X | X | Identify areas where more frequent cleaning is necessary | 80 | Staff Hours | 80 | 0 | 0 | 6400 | 6400 | 6400
| 4a. | Integrated Pesticide, Herbicide, and Fertilizer Management Plan |  |  | X |  |  | Review current landscape policies, including an inventory of pesticides, herbicides, and fertilizers used. | 120 | Staff Hours | 80 | 0 | 0 | 9600 | 0 | 0
| 4b. |  |  |  | X | X |  | Prepare Management Plan outlining alternative methods to reduce use of pesticides and herbicides & establish application rates and methods | 320 | Staff Hours | 120 | 0 | 0 | 38400 | 38400 | 0
| 4c. |  |  |  |  | X |  | Train Public Works employees in the contents of Management Plan | 120 | Staff Hours | 80 | 0 | 0 | 0 | 9600 | 0
| 4d. |  |  |  |  | X | X | Implement of Management Plan on all City properties | 200 | Staff Hours | 80 | 0 | 0 | 0 | 16000 | 16000
TOTAL ANNUAL SWMP IMPLEMENTATION COST | [11 empty] | 307920 | 580840 | 625720 | 594520 | 541720
APPROXIMATE EXISTING STORM WATER BUDGET | [11 empty] | 305000 | 305000 | 305000 | 305000 | 305000
ADDITIONAL STORM WATER BUDGET FUNDING REQUIRED | [11 empty] | 2920 | 275840 | 320720 | 289520 | 236720
Abbreviations:
BMP = Best Management Practice | [7 empty] | O&M = Operation and Maintenance Manual
CUPA = Certified Unified Program Agency | [7 empty] | RCAA = Redwood Community Action Agency
DEH = Humboldt County Division of Environmental Health | [7 empty] | SWMP = Storm Water Management Plan
MCM = Minimum Control Measure