## Monitoring Tasks
Step | Task # | Function Name | Description | Labor Per Event | Phase/Status/# of Times | Responsible Role/Title | Responsible Person's Name | Product | Completion Date
1. Question | 1.1 | Question formulation | Define monitoring questions with input from stakeholders, data users (e.g., Regional Board staff), and possibly with participation of technical experts or a Technical Advisory Committee (TAC) [see comment # 1 on last page] | 6 hrs | Initiation | Technical Leader
| 1.2 |  | Find and establish contact with other entities that are collecting data in the same watershed, and learn about their questions, parameter lists, and methods. |  | Initiation | Technical Leader
2. Study Design | 2.1 | Parameter selection | Create a list, or Parameter Package, of parameters that together make the results of each other more useful; list as field or lab work. Consult with other groups, data users, and technical experts, and add parameters if needed. |  | Initiation | Technical Leader |  | Parameter Package for each question
| 2.2 | Spatial sampling design development | Review maps of the watershed and select multiple locations for sampling, based on a sampling design principle that is appropriate for your question [consult with experts and seek guidance, also see comments # 1 & 2 below] |  |  | Technical Leader
| 2.3 | Station access verification | Determine legal access to the locations you have selected. If needed, contact land owners to develop and secure access agreements [see comment # 2 below]. |  |  | Trainer
| 2.4 | Waterbody reconnaissance | Visit the waterbody (e.g. creek) at multiple legal access points and record all information relevant to your station selection criteria. | 10-16 hrs | Initiation
| 2.5 | Station selection | Revisit monitoring questions and select Stations | 4 hrs | Initiation | Technical Leader
| 2.6 | Station location documentation | Designate a unique Station ID and create a table with description of the exact location of each Station (or fill out the “Location” sheet in the Project File Database). | 1 hr | Initiation | Trainer |  | Station Location table
| 2.7 | Temporal sampling design | Revisit monitoring questions and determine seasonal coverage, monitoring frequency, time of day, etc.) [see comments # 1 & 2 below] | 6 hrs | Initiation
| 2.8 | Statistical power strategy development | Determine the total number of samples, number of replicates, and sample compositing techniques needed to answer question. Consult with experts. |  |  |  |  | Dataset design and power table
3. Data Quality Objectives | 3.1 | Development of measurement quality objectives (MQO's) | Define tolerable error (combined precision and accuracy) and adequate resolution and/or detection limit for each parameter. Consult with data users and technical experts. |  | Initiation |  |  | MQOs for each question and each parameter
| 3.2 | Development of other Data Quality Objectives (DQO's) | Consult with statisticians and data users to set objectives for completeness and to define aspects of comparability or other DQOs related to the Project's datasets. |  |  |  |  | Dataset-specific DQOs
4. Methods | 4.1 | Field methods selection | Explore the sources of error and overall performance of available instruments and kits to be used for field measurements, and select those that will provide results of adequate measurement quality. |  |  | Trainer
| 4.2 |  | Create a summary table for field methods including type (i.e., principle of measurement) and range, detection limit, resolution, and attainable error. |  |  | Trainer |  | Field methods table
| 4.3 | Laboratory methods selection | Select analytical methods to be used for lab analyses that will provide results of adequate measurement quality. |  |  | Trainer
| 4.4 |  | Create an "analytical suite table" (by parameter) for lab methods including method number, analytical principle, and expected performance. |  |  | Trainer |  | Draft Analytical Suite table
5. Written Plans | 5.1 | Development of a Quality Assurance Project Plan (QAPP) | Create a Quality Assurance Project Plan (QAPP) that delineates actions to be taken to control - and assure documentation of - sample integrity, measurement or analysis quality, proficiency or certification of operators, etc. |  |  | Technical Leader
| 5.2 | Assembly of draft Monitoring Plan | Prepare a project-specific monitoring plan [see comment # 2 below]. Include the products from previious tasks (e.g., Questions, Design, Station Location and selection rationale, Parameter Package, mehtods, etc). |  | Initiation | Technical Leader |  | Draft Monitoring Plan
| 5.3 | Monitoring Plan technical review | Submit the Monitoring Plan for an independent review by a technical expert, and receive comments. Respond to comments and refine Monitoring Plan as needed. |  | Initiation | Technical Leader |  | Final Monitoring Plan (for Year 1)
| 5.4 | Preparation of EPA-style QAPP | If needed, develop Quality Assurance Project Plan (QAPP), using EPA and/or SWAMP templates as necessary. Insert elements from your Monitoring plan where appropriate. |  | Initiation | Technical Leader |  | Draft QAPP
| 5.5 | Approval of mandatory QAPP | Submit the QAPP for external review as required for your Project and follow up on the review process until the QAPP is approved. |  |  | Technical Leader |  | Approved QAPP
6. Preperations & Logistics | 6.1 | Selection and purchase of kits, instruments, and standards | Scan catalogues, talk to manufacturers’ sales and tech support staff, or obtain all ordering information from recommendations in guidance documents. Select and order equipment, then assure shipping and payments. |  | Initiation | Trainer
| 6.2 | New Instrument documentation | Fill out the “Instrument/method” and “Standards” sheets in the Project File Database | 30 min | Initiation | Trainer
| 6.3 | Equipment testing | Test all new and borrowed kits, instruments, and sampling equipment. | 4-6 hrs | Initiation | Trainer
| 6.4 | Completion of field kit box | Provide deionized water, trays, paper towels, liquid waste containers, sampling poles, etc. | 2 hrs | Initiation | Trainer
| 6.5 | Tailoring Field data sheet | Prepare a project-specific field data sheet with parameter suite and Instrument Ids |  | Initiation | Trainer
| 6.6 | Communication with Laboratory | Secure the availability of a qualified Project person with adequate background and have them negotiate with lab to clarify all aspects of analyses cost, coordination, and methodology [ask your CWT coordinator for a Lab Check-List]. | 3 hrs | Initiation | Technical Leader |  | Final Analytical Suite table
| 6.7 | Recruitment of Field Operators | Conduct outreach and recruit interested citizens for the monitoring effort. |  | Initiation and ongoing
| 6.8 | Awareness training for Field Operators | Provide “monitoring introduction” to potential field operators regarding monitoring objectives, awareness of error, honest reporting, full documentation, and safety issues. | 4 hrs init. | Initiation and ongoing | Trainer
| 6.9 | Measurement Skills: Training, drilling and testing of Field Operators | Teach operators how to calibrate instruments and keep calibration records, conduct measurements, and fill out the field data sheet. | 4 hrs init. | Initiation x2 and ongoing | Trainer
| 6.10 | Sampling and custody training for field operators | Teach operators how to designate Sample IDs, collect samples, collect field QA/QC samples (dups., blanks etc.), fill chain of custody forms, pack & ship sample containers, etc. |  |  | Trainer
7. Monitoring | 7.1 | Data gathering | Conduct calibrations, accuracy checks, measurements, and sampling. Review all field records for completeness and to see if values “make sense”; repeat measurements if needed. | var | Each event | Field Operator
| 7.2 | Field-notes Custody | Photocopy all field records, secure originals, and mail copies to the Reviewer and to the Trainer | 10 min | Each event | Field Operator
| 7.3 | Field-notes Review | Review all field records for completeness and to see if values “make sense”. Verify re-testing and clarify ambiguous issues with field operators. | 10 min | Each event | Trainer
| 7.4 | Data Entry | Enter all field records (i.e., calibration, observations, and measurement results & documentation) into the designated sheets in the Project File Database | 20 min | Each event | Trainer
| 7.5 | Coordinate sampling & shipping | Receive containers, log samples in Chain of Custody forms, pack and send samples, inform lab. | 30 min | Each event | Trainer
| 7.6 | Kit box maintenance | Purchase DI water, paper towels, batteries etc. as needed |  | ongoing | Field Operator
| 7.7 | Equipment “service” and kit replenishing | Purchase reagents, send faulty equipment for service, replace electrodes, etc. and UPDATE “instrument” sheet in the Project File Database |  | On call | Trainer
| 7.8 | On-call technical support | Answer questions on the phone as needed |  | On call | Technical Leader
| 7.9 | Periodic visits to monitoring events | Conduct field visits with monitoring groups to observe their activities and provide ongoing technical guidance | 4 hrs | Ongoing., 3/yr | Technical Leader
| 7.10 | Formal quality assurance and quality control (QA/QC) events | Purchase/obtain Standard Reference Materials for tested analytes and conduct instrument/kit calibration/testing events and “Round Robin” testing. Enter data, review, summarize, interpret, and report results (see comment # 3 below) | 8 hrs | 2/yr
| 7.11 | Data entry review | Review all sheets of the Project File Database for completeness, spot-check entries against data sheets, clarify and correct as needed. Review (eyeball or plot) the actual data to see if it “makes sense” and verify re-testing by field operators. | 4 hrs | 2/yr
| 7.12 | Review of lab reports | Conduct an independent QA/QC review on lab report (hardcopy or electronic), clarify issues with lab, review corrected lab report |  | Each event | QA/QC officer
| 7.13 | Management of electronic lab data | Receive data files from lab, assure complete documentation and compatibility with Project file, copy and paste data blocks into Project File. |  | Each event | QA/QC officer
| 7.14 | Assessment of Measurement Error | Review all entries of calibration and accuracy checks and calculate error range for each instrument for each monitoring period.
| 7.15 | Data validation and qualifying | Generate data qualifiers for validity, error range, and level of documentation, and enter these descriptors near each Result in the Project File.
| 7.16 | Project File completion | Enter all intent and design information into the Project File, assemble all spreadsheets (including Location, Instruments, etc) and check entire file for completeness.. |  |  |  |  | Draft Project File
8. Reporting | 8.1 | Project QA/QC report chapter | Using the calculated QA/QC endpoints and measures from the previous task, develop a full Project QA/QC report chapter including results of routine calibrations and accuracy checks and results from formal QA/QC events.
| 8.2 | Independent QA/QC review | Submit the Project File and the Project QA/QC report chapter to an independent reviewer, receive comments, respond to comments, and make necessary corrections in the deliverables. |  |  |  |  | Final Project File
| 8.3 | Project summary reporting | Develop an event summary or an annual report and submit to data users with the Project File; provide a presentation of results to data users.
| 8.4 | Presentation of study results | Provide a presentation of project monitoring results and meaning to field operators and other Project participants
9. Second year | 9.1 | Adaptive result evaluation | Revisit questions, monitoring design, parameter package, and DQOs in light of first year findings. | 3 hrs
| 9.2 | Refining of the Monitoring Plan | Modify Question formulation, Parameter selection, Data quality objectives development, and method selection procedures etc. as needed
| 9.3 | Refining of the QAPP
General Notes on the Task List
a. The users of this DQM electronic file of monitoring task list can delete irrelevant tasks and add new tasks, as needed for their specific Project.
b. The Responsible Role/Title is always a Project person (not a TAC member or advisor).
c. Tasks are organized in the same "Roles" hierarchy as the CWT guidance.
d. Tasks within one Role can be delegated, split, or pooled according to Project's personal resources and expertise.
e. Station location considerations include safety & ease of access, sampling access (bank/bridge), depth of pools, representation of creek conditions, etc. as well as other design considerations.
Comments
Comment # 1: If you can, provide the rationale and the names of stakeholders, data users, or technical experts participating in this task.
Comment # 2: Ask your Clean Water Team coordinator about the availability of templates, guidance, or check lists.
Comment # 3: Quality assurance and quality control (QA/QC) are the processes that are implemented throughout the project to assure data quality.