## Sheet1
QADM Kick-Off Meeting Checklist
Prior to Meeting: |  |  |  | X | Notes
Add Project to Projects Table in the SWAMP Database
Review completed COC & AA forms
Review Work Order spreadsheet
a. Are there analytes that don't have SWAMP MQOs/Sample Handling tables?
Yes: Ask in meeting what method will be used and if it contains specific quality control and sample handling requirements. Are field staff trained on required procedures?
b. Check the number of QA duplicates (5% of samples required)
Review appropriate SWAMP SOPs, MQOs and Sample Handling requirements
a. Are there any short holding times? Tricky method procedures to mention?
Review Sampling Schedule
a. Are there any holidays that may effect scheduled sampling days, sample shipment or lab analysis (required holding times)?
Communication Plan:
Is there a communication plan in place in case there are issues?
SWAMP Communication Plan Document
Request that the regional liason be cc'd on any issues
Quality Assurance Questions:
Are personnel trained on required SWAMP field SOP procedures?
Are personnel familiar with SWAMP MQOs, Sample Handling requirements, and holding times?
Are labs SWAMP trained?
Should field blanks be collected?
Should equipment blanks be collected?
Is there a plan for re-sampling if needed?
Is there a sample shipping schedule in place?
Who is responsible for preserving the samples, field crew or lab?
Does the lab need extra volume for QC analysis, how much?
Shipping- Check shipping addresses and courier services for each lab
Data Management Questions:
Have new codes been added to the database and LookUp Lists (if applicable)?
a. Station Codes
b. Funding Codes
c. Device Codes - GPS or otherwise
d. Personnel/Personnel Duty/ Personnel LookUps
When will lab send preliminary preview of data to Regions?
If new lab personnel, do they need training to submit data through SWAMP checker?
Request turn-around for lab analysis
When will data be delivered through SWAMP data checker?
What is the timeline for transferring data from the SWAMP checker to the temp side?
What is the timeline for pushing data from temp to perm side?
What are the procedures for data verification and who is responsible?
QADM Staff to remind project staff on location of QA rules (QA codes, look up list) and who is the QADM staff to contact with questions