## Table 1 Watershed Rotation
HU # | HYDROLOGIC UNIT | YEAR 1 | YEAR 2 | YEAR 3 | YEAR 4 | YEAR 5
|  | 2000-01 | 2001-02 | 2002-03 | 2003-04 | 2004-05
901 | San Juan HU | x | 22 sites | x | x | x
902 | Santa Margarita HU | x | x | 14 sites | x | x
903 | San Luis Rey HU | x | x | x | 13 sites | x
904 | Carlsbad HU | 14 sites | x | x | x | x
905 | San Dieguito HU | x | x | 10 sites | x | x
906 | Peñasquitos HU | 8 sites | x | x | x | x
907 | San Diego HU | x | x | x | 13 sites | x
908 | Pueblo San Diego HU | x | x | x | x | 3 site
909 | Sweetwater HU | x | x | x | x | 10 sites
910 | Otay HU | x | 11 sites | x | x | x
911 | Tijuana HU | x | x | x | x | 12 sites
| Totals | 22 | 33 | 24 | 26 | 25
Number of sites represents identified sites including alternates.

## Table 3.1 00-01 Analyses
FY | # | MONITORING SITE LOCATION | WATER | [5 empty] | SEDIMENT |  | BENTHOS | TISSUE
|  |  | Physico-chemistry* | Conventional Chemistry** | Metals | Organo-chlorine & Organo-phosphate Pesticides & PCBs | Toxicity (7-day Cerio-daphnia) | Toxicity (Selen-estrum) | Sediment Characterization (Grain size and Hydrogen Sulphide) | Toxicity (Hyalella) | Bioassess-ment*** | Fish Tissue Chemistry - Metals | Fish Tissue Chemistry - Pesticides / Aroclors | Fish Tissue Full Scan & PAHs (NIST list)
CARLSBAD HYDROLOGIC UNIT (904)
FY00-01 | 1 | Escondido Creek (ESC1) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 2 | Escondido Creek (ESC5) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 3 | Escondido Creek (ESC8) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 4 | Loma Alta Creek (LAC4) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 5 | San Marcos Creek (SAM3) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 6 | San Marcos Creek (SAM5) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 7 | Encinitas Creek (ENC2) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 8 | Cottonwood Creek (CWC2) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 9 | Aqua Hedionda Creek (AQH1) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 10 | Aqua Hedionda Creek (AQH6) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 11 | Buena Vista Creek (BVR4) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | alt | Loma Alta Creek (LAC3) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | alt | San Marcos Creek (SAM6) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY00-01 | alt | Buena Vista Creek (BVR3) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
LOS PENASQUITOS HYDROLOGIC UNIT (906)
FY00-01 | 12 | Los Penasquitos Creek (LPC4) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | April
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 13 | Los Penasquitos Creek (LPC6) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | April
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 14 | Tecolote Creek (TEC3) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | April
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June
|  |  | October | October | October | October | October | October | October | October
FY00-01 | 15 | Rose Creek (RSC4) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | April
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June
|  |  | October | October | October | October | October | October | October | October
FY00-01 | alt | Poway Creek (POW2) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | April
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June
|  |  | October | October | October | October | October | October | October | October
FY00-01 | alt | Los Penasquitos Creek (LPC4b) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | April
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June
|  |  | October | October | October | October | October | October | October | October
FY00-01 | alt | Tecolote Creek (TEC2) | February | February | February | February | February | February | February | February |  | May/June | May/June | May/June
|  |  | April | April | April | April | April | April | April | April | April
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June
|  |  | October | October | October | October | October | October | October | October
*Physicochemistry: in situ temperature, dissolved oxygen, pH, specific conductance & turbidity
**Conventional chemistry: nutrients (ammonia N, nitrate N, nitrite N, TKN, total P & orthophosphate), sulfate, alkalinity & TSS)
***Bioassessment: benthic macroinvertebrate assemblage (Monitoring performed by NPDES Municipal Storm Water Copermittees)

## Table 3.2 01-02 Analyses
FY | # | MONITORING SITE LOCATION | WATER | [5 empty] | SEDIMENT |  | BENTHOS | TISSUE
|  |  | Physico-chemistry* | Conventional Chemistry** | Metals | Organo-chlorine & Organo-phosphate Pesticides & PCBs | Toxicity (7-day Cerio-daphnia) | Toxicity (Selen-estrum) | Sediment Characterization (Grain size and Hydrogen Sulphide) | Toxicity (Hyalella) | Bioassess-ment*** | Fish Tissue Chemistry - Metals | Fish Tissue Chemistry - Pesticides / Aroclors | Fish Tissue Full Scan & PAHs (NIST list)
SAN JUAN HYDROLOGIC UNIT (901)
FY01-02 | 1 | Aliso Creek just above English Creek | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | 2 | Aliso Creek just below Wood Canyon | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | 3 | Wood Canyon just above Aliso Creek (REF) | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | 4 | San Juan Creek just above tidal influence | February | February | February | February | February | February | February | February |  | June | June | June
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | 5 | Arroyo Trabuco just above San Juan Creek | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | 6 | Arroyo Trabuco just above Holy Jim Canyon | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | 7 | Oso Creek just above Arroyo Trabuco | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | 8 | San Juan Creek just above Bell Canyon (REF) | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | 9 | San Juan Creek just above Canada Gobernadora | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | 10 | San Juan Creek just above Canada Chiquita | February | February | February | February | n/a | n/a | n/a | n/a |  | n/a | n/a | n/a
|  |  | October: April; October: April; October: April; October: April | May/June
|  |  | October: May - June; October: May - June; October: May - June; October: May - June | October
|  |  | October | October | October | October
FY01-02 | 11 | San Mateo Creek just above tidal influence (REF) | February | February | February | February | n/a | n/a | n/a | n/a |  | n/a | n/a | n/a
|  |  | October: April; October: April; October: April; October: April | May/June
October
FY01-02 | 12 | Devil's Canyon Creek above confluence with San Mateo Creek (REF) | February | February | February | February | n/a | n/a | n/a | n/a |  | n/a | n/a | n/a
|  |  | October: April; October: April; October: April; October: April | May/June
October
FY01-02 | 13 | San Mateo Creek above confluence with Devil's Canyon (REF) | February | February | February | February | n/a | n/a | n/a | n/a |  | n/a | n/a | n/a
|  |  | October: April; October: April; October: April; October: April | May/June
October
FY01-02 | 14 | San Onofre Creek just above tidal influence (REF) | February | February | February | February | n/a | n/a | n/a | n/a |  | n/a | n/a | n/a
|  |  | October: April; October: April; October: April; October: April | May/June
October
OTAY HYDROLOGIC UNIT (910)
FY01-02 | 15 | Jamul Creek just above lower Otay Reservoir | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | 16 | Dulzura Creek just above Jamul Creek | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | 17 | Hollenbeck Canyon Creek just above Dulzura Creek | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | alt | Telegraph Canyon Creek (location to be determined) (alternate) | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | May/June
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | October
|  |  | October | October | October | October | October | October | October | October
FY01-02 | alt | Otay River (location to be determined) (alternate) | February | February | February | February | February | February | February | February | n/a | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April
FY01-02 | alt | Pringle Canyon Creek just above Dulzura Creek (alternate) | February | February | February | February | February | February | February | February |  | n/a | n/a | n/a
|  |  | April | April | April | April | April | April | April | April | April
|  |  | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June | May - June
*Physicochemistry: in situ temperature, dissolved oxygen, pH, specific conductance & turbidity
**Conventional chemistry: nutrients (ammonia N, nitrate N, nitrite N, TKN, total P & orthophosphate), sulfate, alkalinity & TSS)
***Bioassessment: benthic macroinvertebrate assemblage (Monitoring performed by NPDES Municipal Storm Water Copermittees)

## Table 4 Other Monitoring
BASIN # | WATERBODY | MONITORING LOCATIONS | DATA / INFORMATION SOURCE | DATA COLLECTED | MONITORING PERIODS | RESPONSIBLE PARTY | RESPONSIBLE PARTY CONTACT | SDRWQCB STAFF CONTACT
SAN JUAN HYDROLOGIC UNIT
901 | Orange County | countywide in SD Region | Tenative Order 2001-193 - Orange County municipal storm water permit | bioassessment, toxicity, water chemistry, nutrients & metals, sed chemistry, metals & organics | storm events, dry weather monitoring, annual reports | Orange County CoPermittees |  | P. Hammer D. Gibson
901 | Orange County coastline | coastline | Bight 1998 Regional Monitoring Program. SCCCWRP | bacteria, water chemistry, toxicity, benthic comm. analyses | Aug 1998 - Sept 1998 | Southern California Coastal Water Research Project | Ken Schiff | Pete Michael Joan Brackin Christina Arias
901 | Orange County coastline | coastline (Laguna Beach, Dana Point, Aliso, San Juan, San Clemente) | Beach Closure/Postings Data 1997-2001. Orange County DEH. AB 1946. | bacteria | storm events, monthly summaries, annual reports | Orange County Dept. of Environmental Health | Monica Mazur, OC DEH (714) 667-3751
901 | San Diego County | countywide | Order 2001-01 - San Diego County municipal storm water permit | bioassessment, toxicity, water chemistry, nutrients & metals, sed chemistry, metals & organics | storm events, dry weather monitoring, annual reports | San Diego County CoPermittees |  | P. Hammer D. Gibson
901.11 |  | Sewage spill receiving water | Emerald Bay Service District WDID 9 000000769 Order No. 96-004 | spill events | spills | Emerald Bay Service District |  | Adam Laputz
901.11 |  | Sewage spill receiving water | Irvine Ranch Water District Sewage Collection System WDID 9 000000772 Order No. 96-004 | spill events | spills | Irvine Ranch Water District |  | Chiara Clemente
901.12 | Laguna Canyon Channel | Station ID LCW102 at Woodland Ave | Annual Progress Report Orange County Municipal Stormwater Permit NPDES CA0108740 Order No. 96-003 | water chemistry, nutrients & metals sed chemistry, metals & organics | annual storm events Mar 1992 - Dec 1995 | Orange County Public Facilities & Resources Dept. | Karen Ashby, OC PFRD (714) 567-6297 | Jeremy Haas
901.13 | Aliso Creek | 2 sites: along Country Club Rd and at Pacific Park Dr/Oso Pkwy | SDRWQCB 1998 surface water sampling s:\wqs\303dlist\linda_pardy.xls | water chemistry nutrients metals | 1998-06-10 | SDRWQCB | Linda Pardy, SDRWQCB pardl@swrcb.ca.gov Greig Peters, SDRWQCB peteg@swrcb.ca.gov | Linda Pardy
901.13 | Aliso Creek | 3 riffles upstrm of Pacific Park Dr. 5 riffles parallel to Country Club Rd upstrm of Hwy 1. | SDRWQCB 1999 Biological Assessment Annual Report. CA Dept. of Fish & Game | benthic macroinvertebrate indices | May, Sep & Nov 1998, May 1999 for most sites | SDRWQCB CA DFG | James M. Harrington jharring@ospr.dfg.ca.gov (916) 358-2858 | David Gibson Linda Pardy Lisa Brown
901.13 | Aliso Creek | 5 sites: at Cooks Corner, d/s English Cyn, d/s Dairy Fork & Aliso Hills Ch., d/s Sulphur Creek, @ PCH Bridge | Aliso Creek 205j Water Quality Planning Study.Orange County, PFRD & Tetra Tech. Agreement No. 7-042-250-0. June 2000 | flow water chemistry bacteria temperature aquatic life bioassessment toxicity | Sept 1998 - Jan 2000 | Orange County Public Facilities & Resources Dept. | Karen Ashby, OC PFRD (714) 567-6297 | Jeremy Haas
901.13 | Aliso Creek | at Pacific Park Dr | Toxics Substance Monitoring Program Data Report. SWRCB Div of Water Quality. 1999 | organics & metals in fish tissue | annual Aug 1999 | SWRCB DWQ SDRWQCB CA DFG | Del Rassmussen DWQ SWRCB | Linda Pardy
901.13 | Aliso Creek | Station ID ACJ01 in Laguna Wood Canyon Wilderness Park | Annual Progress Report Orange County Municipal Stormwater Permit NPDES CA0108740 Order No. 96-003 | water chemistry, nutrients & metals sed chemistry, metals & organics | annual storm events Sept 1991 - June 2000 | Orange County Public Facilities & Resources Dept. | Karen Ashby, OC PFRD (714) 567-6297 | Jeremy Haas
901.13 | Aliso Creek Watershed | Aliso Creek Watershed (Aliso Creek, Sulphur, etc.) | San Juan & Aliso Creeks Watershed Management Study Reconnaissance Report. Orange Coutny, CA. US Army Corps of Engineers, Los Angeles District. February 1997. | hydrology, hydraulics, water chemisty, geomorphology, sediment yields, economics | 1992 - 1995 | US Army Corps of Engineers, Los Angeles District |  | Jeremy Haas
901.13 | Aliso Creek Watershed | Aliso Creek Watershed (Aliso Creek, Sulphur, etc.) | Aliso Creek Watershed Management Study Draft Feasibility Report. US Army Corps of Engineers, Los Angeles District. May 1999. | planning info, hydrology, hydraulics, water quality, geomorphology, sediment info, economics | 1999-05-01 | US Army Corps of Engineers, Los Angeles District |  | Jeremy Haas
901.13 | Aliso Creek Watershed | storm drain outfalls and receiving waters | Quarterly Progress Report. SDRWQCB Directive Issued Pursuant to California Water Code Section 13225 | bacteria flow chlorine pH | 2001-07-31 | County of Orange Orange County Flood Control District City of Aliso Viejo City of Laguna Beach City of Laguna Hills City of Laguna Niguel City of Laguna Woods City of Lake Forrest City of Mission Viejo | Karen Ashby, OC PFRD (714) 567-6297 | Jeremy Haas
901.13 | Pacific Ocean | POTW effluent receiving water | Aliso Ocean Outfall NPDES CA0107611 WDID 9 000000117 Order No. 95-107 | effluent receiving water water chemistry bacteria toxicity | monthly | Aliso Water Management Agency |  | Adam Laputz
901.13 | Sulphur Creek | Station ID SCDAM located downstream of Sulphur Creek dam | Annual Progress Report Orange County Municipal Stormwater Permit NPDES CA0108740 Order No. 96-003 | water chemistry, nutrients & metals sed chemistry, metals & organics | annual storm events Mar 1992 - Apr 1996 | Orange County Public Facilities & Resources Dept. | Karen Ashby, OC PFRD (714) 567-6297 | Jeremy Haas
901.13 |  | POTW effluent receiving water | Fwy Forcemain Replacement DW NPDES CAG919002 WDID 9 000000905 Order No. 96-041 |  | monthly | El Toro Water District |  | W. Ghoram
901.13 |  | Sewage spill receiving water | El Toro Water District Sewage Collection System WDID 9 000000768 Order No. 96-004 | spill events | spills | El Toro Water District |  | Adam Laputz
901.13 |  | Sewage spill receiving water | Laguna Beach Sewage Collection System WDID 9 000000753 Order No. 96-004 | spill events | spills | City of Laguna Beach |  | Adam Laputz
901.13 |  | Sewage spill receiving water | Los Alisos Water District Sewage Collection System WDID 9 000000774 Order No. 96-004 | spill events | spills | Los Alisos Water District |  | Adam Laputz
901.13 |  | Industrial effluent receiving water | Glass Canyon Facility WDID 9 000000140 Order No. 95-056 |  | annual | El Toro Material Company |  | C. Komeylyan S. Knedik
901.13 |  | POTW effluent receiving water SOCRA outfall | South Coast County Water District Water Reclamation Plant WDID 9 000000172 Order No. 97-052 |  |  | SOCRA / South Coast County Water District |  | Adam Laputz
901.14 |  | POTW effluent receiving water | PLANT 3-A WDID 9 000000352 Order No. 97-052 | monthly |  | SOCRA / Moulton Niguel Water District |  | Adam Laputz
901.14 | Dana Point Harbor | Industrial effluent receiving water | Dana Point Shipyard NPDES CA109312 WDID 9 000000219 Order No. 00-216 |  | quarterly | Dana Point Shipyard |  | C. Komeylyan
901.14 | Dana Point Harbor | Station IDs DAPTEB, DAPTWB, DAPLTR, DAPTLB, DAPTHE (outfalls, boatyards) | Annual Progress Report Orange County Municipal Stormwater Permit NPDES CA0108740 Order No. 96-003 | water chemistry, nutrients & metals sed chemistry, metals & organics | annual storm events Sept 1991 - June 2000 | Orange County Public Facilities & Resources Dept. | Karen Ashby, OC PFRD (714) 567-6297 | Jeremy Haas
901.14 |  | POTW effluent receiving water | Joint Regional Water Reclamation Facility WDID 9 000000118 Order No. 97-052 | monthly |  | SOCRA / Moulton Niguel Water District |  | Adam Laputz
901.14 |  | Sewage spill receiving water | South Coast County Water District WDID 9 000000784 Order No. 96-004 | spill events | spills | South Coast County Water District |  | Adam Laputz
901.2 |  | Industrial effluent receiving water | Mission Viejo Sand Plant WDID 9 000000079 Order No. 88-055 |  | semi-annual | Oglebay Norton Industrial Sand |  | C. Komeylyan S. Knedik
901.2 |  | Landfill receiving water | Forster Canyon Landfill WDID 9 000000586 Order No. 94-106 | Landfill leachate? Groundwater? Surface water? |  | San Juan Meadows LP
901.2 |  | POTW effluent receiving water | Nichols Research Institute Water Reclamation Facility WDID 9 000000502 Order No. 97-052 | monthly |  | SOCRA / Santa Magrarita Water District |  | Adam Laputz
901.2 |  | POTW effluent receiving water | Oso Creek Water Reclamation Facility WDID 9 000000114 Order No. 97-052 | monthly |  | SOCRA / Santa Magrarita Water District |  | Adam Laputz
901.2 |  | POTW effluent receiving water | Robinson Ranch Water Reclamation Facility WDID 9 000000078 Order No. 97-052 |  |  | SOCRA / Trabuco Canyon Water District |  | Adam Laputz
901.2 |  | POTW effluent receiving water Reclaimed water use for landscape irrigation and groundwater recharge | Joplin Youth Center WDID 9 000000073 Order No. 93-047 | water chemistry | monthly | Orange County Probation Dept. |  | Adam Laputz
901.2 |  | POTW effluent receiving water Reclaimed water use for landscape irrigation and groundwater recharge | Los Pinos Forrestry Camp WDID 9 000000075 Order No. 94-046 | water chemistry | monthly | Orange County Probation Dept. |  | Adam Laputz
901.2 |  |  | Ortega Oaks Campground WDID 9 000000131 Order No. 88-063 |  |  | Progresive Managment
901.2 | Arroyo Trabuco Creek | Station ID TCOL02 | Annual Progress Report Orange County Municipal Stormwater Permit NPDES CA0108740 Order No. 96-003 | water chemistry, nutrients & metals sed chemistry, metals & organics | annual storm events Mar 1994 - May 1999 | Orange County Public Facilities & Resources Dept. | Karen Ashby, OC PFRD (714) 567-6297 | Jeremy Haas
901.2 | Arroyo Trabuco Creek | Trabucco/Holy Jim Station IDs HJT #1-9 | USDA Forest Service Sampling Report |  | June 1998 Oct 1998 | US Dept of Agriculture Forest Service | Ron Wright, Forest Soil Scientist (760) 788-0250 x 3337 rgwright@fs.fed.us | Jimmy Smith Linda Pardy
901.2 | San Juan Creek Watershed | San Juan Creek Watershed (San Juan Creek, Oso Creek, Bell Canyon Trabuco, etc.) | San Juan & Aliso Creeks Watershed Management Study Reconnaissance Report. Orange Coutny, CA. US Army Corps of Engineers, Los Angeles District. February 1997. | hydrology, hydraulics, water chemistry, geomorphology, sediment yields, economics | 1992 - 1995 | US Army Corps of Engineers, Los Angeles District |  | Jeremy Haas
901.2 | San Juan Creek Watershed | San Juan Creek Watershed (San Juan Creek, Oso Creek, Bell Canyon Trabuco, etc.) | San Juan Watershed Study Feasibility Phase Draft Watershed Management Report. US Army Corps of Engineers, Los Angeles District. December 1999. | planning info, hydrology, hydraulics, water quality, geomorphology, sediment info, economics | 1999-12-01 | US Army Corps of Engineers, Los Angeles District |  | Jeremy Haas
901.21 | Oso Creek | Mission Viejo Golf Course irrigation runoff | submitted data | water chemistry | Jan 1998 - Jan 2001 | Santa Margarita Water District | Bob Jordan, SMWD bobj@smwd.com
901.21 | Oso Creek | Station ID OSOL03 at Crown Valley Parkway | Annual Progress Report Orange County Municipal Stormwater Permit NPDES CA0108740 Order No. 96-003 | water chemistry, nutrients & metals sed chemistry, metals & organics | annual storm events Aug 1991 - May 1999 | Orange County Public Facilities & Resources Dept. | Karen Ashby, OC PFRD (714) 567-6297 | Jeremy Haas
901.22 | San Juan Creek | Station ID 11046530, 20 ft downstream from La Novia Street Bridge, 1.3 mi upstream from Arroyo Trabuco Creek | http://ca.water.usgs.gov http://s601dcascr.wr.usgs.gov/Sites/h1807.html | flow | hourly | US Geologic Survey Dept. | Patricia A Shiffer (916) 278-3100 pshiffer@usgs.gov
901.25 | San Juan Creek | San Juan/Hot Springs Station IDs SJH #1-7 | USDA Forest Service Sampling Report | bacteria nutirents pH flow | June 1998 Oct 1998 | US Dept of Agriculture Forest Service | Ron Wright, Forest Soil Scientist (760) 788-0250 x 3337 rgwright@fs.fed.us | Jimmy Smith Dave Gibson Linda Pardy
901.25 thru 901.28 | San Juan Creek | 5 riffles upstream of Hwy 74 | SDRWQCB 1999 Biological Assessment Annual Report. CA Dept. of Fish & Game | benthic macroinvertebrate indices | May, Sep & Nov 1998, May 1999 for most sites | SDRWQCB CA DFG | James M. Harrington jharring@ospr.dfg.ca.gov (916) 358-2858 | David Gibson Linda Pardy Lisa Brown
901.25 thru 901.28 | San Juan Creek | at Arroyo Trabuco Creek. 5 riffles w/in Gravel Yard at end of Avery Parkway 5 riffles upstream of Hwy 74 | SDRWQCB 1999 Biological Assessment Annual Report. CA Dept. of Fish & Game | benthic macroinvertebrate indices | May, Sep & Nov 1998, May 1999 for most sites | SDRWQCB CA DFG | James M. Harrington jharring@ospr.dfg.ca.gov (916) 358-2858 | David Gibson Linda Pardy Lisa Brown
901.25 thru 901.28 | San Juan Creek | Station ID SJNL01at La Nova and Station ID SJOL01 at Ortega | Annual Progress Report Orange County Municipal Stormwater Permit NPDES CA0108740 Order No. 96-003 | water chemistry, nutrients & metals sed chemistry, metals & organics | Feb 1992 - May 2000 | Orange County Public Facilities & Resources Dept. | Karen Ashby, OC PFRD (714) 567-6297 | Jeremy Haas
901.27 | Pacific Ocean | POTW effluent receiving water | SERRA Ocean Outfall NPDES CA0107611 WDID 9 000000119 Order No. 00-013 | effluent & receiving water water chemistry bacteria toxicity | monthly | South East Regional Reclamation Authority |  | Adam Laputz
901.27 | San Juan Creek | San Juan Creek at Camino Capistrano | Toxics Substance Monitoring Program Preliminary Data Report. SWRCB Div of Water Quality. 2000 | organics & metals in fish tissue | annual Jul 2000 | SWRCB DWQ SDRWQCB CA DFG | Del Rassmussen DWQ SWRCB | Linda Pardy
901.27 |  | Industrial effluent receiving water | Sta 18-372 Remed NPDES CAG919002 WDID 9 000000887 Order No. 96-041 |  | monthly | Mobil Oil Corp. |  | W. Ghoram
901.3 |  | Landfill receiving water | Prima Deschecha Sanitary Landfill WDID 9 000000261 Order No. 89-102/93-086 | Landfill leachate? Groundwater? Surface water? |  | Orange County Waste Management Dept.
901.3 |  | POTW effluent receiving water Reclaimed water use | San Clemente WRP WDID 9 000000290 Order No. 91-050 | SERRA Outfall | monthly | City of San Clemente |  | Adam Laputz
901.31 | Prima Deshecha | Creek enters ocean 100' south of S15 | South East Regional Reclamation Authority (SERRA) monitoring |  | June 2000 - Jan 2001 and earlier | South East Regional Reclamation Authority |  | Jeremy Haas
901.31 | Prima Deshecha | Station ID PDCM01 at Calle Grande Vista | Annual Progress Report Orange County Municipal Stormwater Permit NPDES CA0108740 Order No. 96-003 | water chemistry, nutrients & metals sed chemistry, metals & organics | annual storm events Aug 1991 - June 2000 | Orange County Public Facilities & Resources Dept. | Karen Ashby, OC PFRD (714) 567-6297 | Jeremy Haas
901.31 | Segunda Deshecha | Creek enters ocean 200' north of S17 | South East Regional Reclamation Authority (SERRA) monitoring |  | June 2000 - Jan 2001 and earliar | South East Regional Reclamation Authority |  | Jeremy Haas
901.31 | Segunda Deshecha | Station ID SDCM02 at El Camino Real | Annual Progress Report Orange County Municipal Stormwater Permit NPDES CA0108740 Order No. 96-003 | water chemistry, nutrients & metals sed chemistry, metals & organics | annual storm events Aug 1991 - June 2000 | Orange County Public Facilities & Resources Dept. | Karen Ashby, OC PFRD (714) 567-6297 | Jeremy Haas
901.31 |  | Sewage spill receiving water | San Clemente Collection System WDID 9 000000758 Order No. 96-004 | spill events | spills |  |  | Adam Laputz
901.4 | San Mateo Watershed | San Mateo Watershed | USDA Forest Service Watershed Study (see letter 5/14/01 letter to K. Cole re: 303d) | floodplain connectivity water quality water quantity steam corridor vegetation channel stabilization aquatic integretity GIS-hydrology, geology | Summer 2001 | US Dept of Agriculture Forest Service | Ron Wright, Forest Soil Scientist (760) 788-0250 x 3337 rgwright@fs.fed.us | Jimmy Smith Dave Gibson Linda Pardy
901.4 | San Mateo Creek | Station ID 11046300, on Camp Joseph H. Pendleton Naval Reservation, 0.4 mi downstream from mouth of Devil Canyon | Disc 1: LAW - Crandall |  | 1997-12-01 | Camp Pendleton Office of Water Resources | Lawrence E. Carlson | Bruce Posthumous Lisa Brown
901.4 | San Mateo Creek | Station ID 11046300, on Camp Joseph H. Pendleton Naval Reservation, 0.4 mi downstream from mouth of Devil Canyon | http://ca.water.usgs.gov http://s601dcascr.wr.usgs.gov/Sites/h1807.html | flow | hourly | US Geologic Survey Dept. | Patricia A Shiffer (916) 278-3100 pshiffer@usgs.gov
901.4 |  |  | TRW Space Technology Labs WDID 9 000000290 Order No. 94-078 |  |  | TRW, Systems Group
901.5 |  | POTW effluent receiving water | PLANT #s 10 & 11 WDID 9 000000034 Order No. 97-013 |  |  | USMC Camp Pendleton |  | Chiara Clemente
901.5 |  | Landfill receiving water | Camp Pendleton Bioremediation Facility WDID 9 000000692 Order No. 95-109 | Landfill leachate? Groundwater? Surface water? |  | USMC Camp Pendleton |  | B. Griffey
901.51 |  | Landfill receiving water | San Onofre Sanitary Landfill WDID 9 000000012 Order No. 2000-08 | Landfill leachate? Groundwater? Surface water? |  | USMC Camp Pendleton |  | B. Griffey
901.51 | Pacific Ocean | Industrial effluent receiving water | SONGS UNIT 1 NPDES CA0001228 WDID 9 000000086 Order No. 00-004 |  |  | Southern California Edison |  | H. Navrozdi
901.51 |  | Industrial effluent receiving water | SONGS UNIT 2 NPDES CA0108073 WDID 9 000000087 Order No. 99-047 |  |  | Southern California Edison |  | H. Navrozdi
901.51 |  | Industrial effluent receiving water | SONGS UNIT 3 NPDES CA0108181 WDID 9 000000088 Order No. 99-048 |  |  | Southern California Edison |  | H. Navrozdi
901.52 |  | Landfill receiving water | Las Pulgas Sanitary Landfill WDID 9 000000013 Order No. 2000-54 | Landfill leachate? Groundwater? Surface water? |  | USMC Camp Pendleton |  | B. Griffey
901.52 |  | POTW effluent receiving water | PLANT #9 WDID 9 000000792 Order No. 98-004 |  |  | USMC Camp Pendleton |  | Chiara Clemente
OTAY HYDROLOGIC UNIT (910)
910 | San Diego Bay | NASSCO & SW Marine Leaseholds | 13267 Guidelines for Assessment and remediation of Contaminated Sediments in San Diego Bay at NASSCO and SW Marine Shipyards | water chemistry toxicity benthic comm. analyses fish tissue analyses | Aug 2001 - May 2002 | NASSCO & SW Marine | Steve Bay, SCCWRP | A. Monji T.Alo
910 | San Diego Bay | Naval Station 7th Street and Paletta Creeks | US Navy Phase I Contaminated Sediment Quality Assessment Study at Chollas Creek and Paleta Creek - Sampling and Analysis Plan | water chemistry toxicity benthic comm. analyses fish tissue analyses | Aug 2001 - May 2002 | US Navy Southern California Coastal Water Research Project | Steve Bay, SCCWRP Bart Chadwick, SPAWAR US Navy | A. Monji T.Alo
910 | San Diego Bay |  | Bight 1998 Regional Monitoring Program. SCCCWRP | bacteria water chemistry toxicity benthic comm. analyses | Aug 1998 - Sept 1999 | Southern California Coastal Water Research Project | Steve Bay, SCCWRP | A. Monji T.Alo
910 | San Diego County | countywide | Order 2001-01 WDRs for Discharges of Urban Runoff from the Municipal Separate Storm Sewers draining the Watersheds of the County of San Diego, Incorporated Cities of San Diego and the San Diego Unifeid Port District | bioassessment, toxicity, water chemistry, nutrients & metals sed chemistry, metals & organics | storm events, dry weather monitoring, annual reports | San Diego County CoPermittees |  | P. Hammer D. Gibson
910.1 | San Diego Bay | Industrial effluent receiving water | SW Quadrant Storm Drain Improvement NPDES No. CAG919002 WDID 9 000000734 Order No. 00-090 |  |  | City of Coronado
910.1 | San Diego Bay | Industrial effluent receiving water | Construction Dewatering NPDES No.CAG919002 WDID 9 000000881 Order No. 00-090 |  |  | Jim Rodolph Residence
910.1 | San Diego Bay | Industrial effluent receiving water | Grove Ave Pump Station Dwt NPDES No.CAG919002 WDID 9 000000892 Order No. 00-090 |  |  | City of San Diego
910.1 | San Diego Bay |  | Homeporting Project Dredging WDID 9 000000689 Order No. 95-118 |  |  | US Navy
910.1 |  | Sewage spill receiving water | Coronado Collection System WDID 9 000000745 Order No. 96-004 | spill events | spills | City of Coronado
910.1 |  |  | NASNI Bioremediation Facility WDID 9 000000686 Order No. 96-018 | Landfill leachate? Groundwater? Surface water? |  | US Navy
910.1 |  | Landfill receiving water | Golf Course Landfill WDID 9 000000819 Order No. 97-011 | Landfill leachate? Groundwater? Surface water? |  | US Navy
910.1 |  | Landfill receiving water | Old Spanish Bight Landfill WDID 9 000000821 Order No. 97-011 | Landfill leachate? Groundwater? Surface water? |  | US Navy
910.2 | Otay River |  | Toxics Substance Monitoring Program Preliminary Data Report. SWRCB Div of Water Quality. 1997 | organics & metals in fish tissue | annual Jun 1997 | SWRCB DWQ SDRWQCB CA DFG | Del Rassmussen DWQ SWRCB | Linda Pardy
910.2 | Otay River |  | Otay Valley 319(h) Regional Park Public Education Project.Coutny of San Diego Dept. of Parks & Recreation. |  | Mar 1998 - May 2001 | County of San Diego Dept. of Parks & Recreation |  | Linda Pardy
910.2 | San Diego Bay | Industrial effluent receiving water | South Bay Power Plant NPDES CA0001368 WDID 9 000000091 Order No. 96-005 |  |  | Duke Energy, LLC |  | P. Richter
910.2 |  | Sewage spill receiving water | Chula Vista Collection System WDID 9 000000744 Order No. 96-004 | spill events | spills | City of Chula Vista
910.2 | Otay River |  | Otay Plant WDID 9 000000158 Order No. 94-007 |  |  | Nelson & Sloan
910.2 |  | Landfill receiving water | Omar Rendering Landfill WDID 9 000000215 Order No. 97-040 | Landfill leachate? Groundwater? Surface water? |  | Darling Intl.
910.2 |  | Landfill receiving water | Otay Annex Sanitary Landfill WDID 9 000000214 Order No. 90-009 / 93-086 | Landfill leachate? Groundwater? Surface water? |  | Allied Waste Industries, Inc.
910.2 |  | Landfill receiving water | Otay Class 1 Landfill WDID 9 000000213 Order No. 2000-161 | Landfill leachate? Groundwater? Surface water? |  | San Diego County Dept of Public Works IWSM
910.3 | Otay Reservoir |  | Lower Otay Lake County Park WDID 9 000000212 Order No. 94-109 |  |  | San Diego County Park & Recreation
910.3 |  |  | BioSolids Application in San Diego County WDID 9 000000766 Order No. 97-032 |  |  | Wheelabrator Water Technology
910.31 | Lower Otay Reservoir | reservoir | data files submitted by City of San Diego | water chemistry metals, organics, nutrients bacteria | weekly | City of San Diego | Jeff Pasek/Ron Coss, City of San Diego | D. Gibson
910.31 |  |  | Fenton Janal Ranch WDID 9 000000422 Order No. 88-084 |  |  | KELCO, Monsanto Company
910.34 |  |  | Indian Hills Campground WDID 9 000000103 Order No. 94-131 |  |  | Shiloah Springs Bible Retreat
910.36 |  |  | Pio Pico Reserve WDID 9 000000044 Order No. 84-006 |  |  | Thousand Trails, Inc.

## Table 5 FY 00-01 Budget
Task Order worksheet for FY 2000-01 SWAMP funds for San Diego Region (R9) as of October 1, 2001 |  | Total units | Total cost per sampling event/round | Number of sampling events/rounds | Grand Total cost for FY00-01 | 5% field dupes/# of sampling events | cost of 5% field dupes
Analysis or Service Performed | Unit Cost
Fieldwork--collection of sediment and/or water samples
Sample collection--sediment and/or water | 500 | 15 | 7500 | 4 | 30000 | 4 | 2000
Includes collection of sediment and/or water at walk-in site, & multiparameter probe
measures (D.O., pH, depth, temp, conductivity, turbidity), and centroid flow measure.
Assumes sample collection site can be accessed fairly close by with vehicle.
Sample shipping (water) | 70 | 15 | 1050 | 4 | 4200 | 4 | 280
Sample shipping (sediment) | 70 | 15 | 1050 | 4 | 4200 | 4 | 280
Fieldwork--collection of tissue (bivalves/fish)
Sample collection--fish (tsm-style) | 1749 | 3 | 5247 | 1 | 5247
Analytical laboratory services
Water chemistry (dissolved metals) | 219 | 15 | 3285 | 4 | 13140 | 4 | 876
Elements included in ICPMS tiss metals suite: | Al, Cr, Mn, Ni, Cu, Zn, Ag, Cd, Pb, As, Se--11 total
ICPMS trace metals suite for water cost includes: sample filter ($20) + sample digest ($10)
+ 1st ICPMS element ($79) + 10 add'tl elements (10x$11) = $219
Water chemistry (Pesticides, PCB's, PAH's) | 798 | 15 | 11970 | 4 | 47880 | 4 | 3192
Tissue chemistry (metals) | 324 | 4 | 1296 | 1 | 1296
Elements included in ICPMS tiss metals suite: | Al, Cr, Mn, Ni, Cu, Zn, Ag, Cd, Pb, As, Se--11 total
ICPMS trace metals suite for tissue cost includes: sample prep (dissect & homogenize) at $79
+ sample digest ($56) + 1st ICPMS element ($79) + 10 add'tl elements (10 x $11) = $324
Tissue chemistry (Pesticides and PCB's) | 830 | 4 | 3320 | 1 | 3320
Conventional constituents in water
Total phosphate | 38 | 15 | 570 | 4 | 2280 | 4 | 152
Ortho-phosphate | 27 | 15 | 405 | 4 | 1620 | 4 | 108
Total Ammonia | 25 | 15 | 375 | 4 | 1500 | 4 | 100
Nitrate | 27 | 15 | 405 | 4 | 1620 | 4 | 108
Total Keldjahl Nitrogen (TKN) | 45 | 15 | 675 | 4 | 2700 | 4 | 180
Sulfate | 27 | 15 | 405 | 4 | 1620 | 4 | 108
Alkalinity | 15 | 15 | 225 | 4 | 900 | 4 | 60
Sediment Characterization
Sediment grain size (% fines only) | 55 | 15 | 825 | 4 | 3300 | 4 | 220
Toxicity testing: UCD Granite Canyon Lab
Sediment toxicity Hyalella 10-day | 840 | 15 | 12600 | 4 | 50400
Freshwater Toxicity 7-d Ceriodaphnia | 683 | 15 | 10245 | 4 | 40980
Freshwater Toxicity Selanestrum | 575 | 15 | 8625 | 4 | 34500
Rapid Bioassessment technical assistance | 14450 | 1 | 6073 | 1 | 3641
(Actual cost is $14,450, and R9 will make-up shortfall of $10,809 out of FY01-02 allocation)
Field QA/QC 5% field duplicates | 7664 |  | 7664 |  | 7664 |  | 7664
(with 15 samples per round, one field dupe/round of each analysis)
R9 share of pass-thru subcontract fee | 3643 | 1 | 3643 | 1 | 3643
Grand Total all costs FY00-01 |  |  |  |  | 265651
Total R9 monitoring allocation FY00-01 |  |  |  |  | 267400
Unallocated |  |  |  |  | 1749

## Table 6 FY01-02 Budget
Task Order worksheet for FY 2001-02 SWAMP funds for San Diego Region (R9) as of October 1, 2001 |  | Total units | Total cost per sampling event/round | Number of sampling events/rounds | Grand Total cost for FY01-02 | 5% field dupes/# of sampling events | cost of 5% field dupes
Analysis or Service Performed | Unit Cost
Fieldwork--collection of sediment and/or water samples
Sample collection--sediment and/or water | 500 | 15 | 7500 | 4 | 30000 | 4 | 2000
Includes collection of sediment and/or water at walk-in site, & multiparameter probe
measures (D.O., pH, depth, temp, conductivity, turbidity), and centroid flow measure.
Assumes sample collection site can be accessed fairly close by with vehicle.
Sample shipping (water) | 70 | 15 | 1050 | 4 | 4200 | 4 | 280
Sample shipping (sediment) | 70 | 15 | 1050 | 4 | 4200 | 4 | 280
Fieldwork--collection of tissue (bivalves/fish)
Sample collection--fish (tsm-style) | 1749 | 4 | 6996 | 1 | 6996
Analytical laboratory services
Water chemistry (dissolved metals) | 219 | 10 | 2190 | 4 | 8760 | 4 | 876
Elements included in ICPMS tiss metals suite: | Al, Cr, Mn, Ni, Cu, Zn, Ag, Cd, Pb, As, Se--11 total
ICPMS trace metals suite for water cost includes: sample filter ($20) + sample digest ($10)
+ 1st ICPMS element ($79) + 10 add'tl elements (10x$11) = $219
Water chemistry (Pesticides, PCB's, PAH's) | 798 | 10 | 7980 | 4 | 31920 | 4 | 3192
Tissue chemistry (metals) | 324 | 4 | 1296 | 1 | 1296
Elements included in ICPMS tiss metals suite: | Al, Cr, Mn, Ni, Cu, Zn, Ag, Cd, Pb, As, Se--11 total
ICPMS trace metals suite for tissue cost includes: sample prep (dissect & homogenize) at $79
+ sample digest ($56) + 1st ICPMS element ($79) + 10 add'tl elements (10 x $11) = $324
Tissue chemistry (Pesticides and PCB's) | 830 | 4 | 3320 | 1 | 3320
Conventional constituents in water
Total phosphate | 38 | 15 | 570 | 4 | 2280 | 4 | 152
Ortho-phosphate | 27 | 15 | 405 | 4 | 1620 | 4 | 108
Total Ammonia | 25 | 15 | 375 | 4 | 1500 | 4 | 100
Nitrate | 27 | 15 | 405 | 4 | 1620 | 4 | 108
Total Keldjahl Nitrogen (TKN) | 45 | 15 | 675 | 4 | 2700 | 4 | 180
Sulfate | 27 | 15 | 405 | 4 | 1620 | 4 | 108
Alkalinity | 15 | 15 | 225 | 4 | 900 | 4 | 60
TSS | 15 | 15 | 225 | 4 | 900 | 4 | 60
Sediment Characterization
Sediment grain size (% fines only) | 55 | 15 | 825 | 4 | 3300 | 4 | 220
Toxicity testing: UCD Granite Canyon Lab
Sediment toxicity Hyalella 10-day | 840 | 15 | 12600 | 4 | 50400
Freshwater Toxicity 7-d Ceriodaphnia | 683 | 15 | 10245 | 4 | 40980
Freshwater Toxicity Selanestrum | 575 | 15 | 8625 | 4 | 34500
Rapid Bioassessment technical assistance | 14450 | 1 | 6073 | 1 | 10809
(Actual cost is $14,450, and R9 will make-up shortfall of $10,809 out of FY01-02 allocation)
Field QA/QC 5% field duplicates | 7724 |  |  |  | 7724 |  | 7724
(with 15 samples per round, one field dupe/round of each analysis)
R9 share of pass-thru subcont & logistics fee | 9773 | 1 | 9773 | 1 | 5524
Note: R9 will owe $4,249 off the top of R9's FY02-03 DFG
SWAMP Task Order, since actual cost of this item is
$9,773, but only $5,524 is allocated here.
Grand Total all costs FY01-02 |  |  |  |  | 257069 |  |  | Funding for
2001-2002
Total R9 monitoring allocation FY01-02 |  |  |  |  | 257069 |  |  | 257069
Unallocated FY01-02 Funds |  |  |  |  | 0